TABLE OF CONTENTS

1.	Budget procedure	3

1.1.	Preliminary Draft Budget (PDB) 2010	3

1.2.	Draft Budget (DB) 2010	3

1.3.	Amending Letter (AL) 2010	3

1.4.	The adoption of the 2010 Budget	3

2.	Management of appropriations	4

2.1.	Management of Commitment appropriations	4

2.1.1.	EAFRD operational programmes	4

2.1.2.	Technical assistance	4

2.2.	Management of payment appropriations	5

2.2.1.	EAFRD operational programmes	5

2.2.2.	Technical assistance	5

3.	The implementation of the 2010 EAFRD budget	6

3.1.	Introduction	6

3.2.	Implementation of commitment appropriations	6

3.2.1.	EAFRD operational programmes	6

3.2.2.	Technical assistance	7

3.3.	Implementation of payment appropriations	7

3.3.1.	EAFRD operational programmes	7

3.3.2.	Technical assistance	12

3.4.	Analysis of expenditure declared by axis and by measure	12

3.5.	Implementation rate of EAFRD programmes	14

# Budget procedure

## Preliminary Draft Budget (PDB) 2010

The 2010 Preliminary Draft Budget (PDB) was adopted by the Commission and proposed to the Budgetary Authority on 29 April 2009.

The proposal for the European Agricultural Fund for Rural Development (EAFRD) under heading 2 of the Financial Framework 2007-2013 totalled 
EUR  13 970 million in commitment appropriations and EUR 12 648 million in payment appropriations (of which EUR 300 million entered in reserve for the European Economic Recovery Package -EERP).

| Budget Item | Commitment appropriations (in €) | Payment appropriations (in €) |
| --- | --- | --- |
| 05.040501 (Rural dev. programmes) | 13 947 136 182 | * 12 639 000 000 |
| 05.040502 (Technical assistance) | 22 548 451 | 9 000 000 |
| *EUR 300 000 000 entered in reserve for the EERP |  |  |

## Draft Budget (DB) 2010

The Council adopted the 2010 Draft Budget in July 2009. The payment appropriations for EAFRD programmes were reduced by EUR 98.0 million as compared to the PDB.

## Amending Letter (AL) 2010

In October 2009 the Commission adopted Amending Letter No 2 to the 2010 PDB. Even though the Amending Letter exercise mainly concerns the EAGF, the commitment appropriations for EAFRD programmes were modified to reflect an additional funding for a total net amount of EUR 388.4 million. This net amount relates to the second part of the EERP, the non application of voluntary modulation in Portugal and a minor adjustment of compulsory modulation in Spain. Payment appropriations decreased by EUR 32.8 million to take account of the non application of volontary modulation in Portugal.

## The adoption of the 2010 Budget

The Council second reading, adopted on 20.11.2009, did not involve any modification of the EAFRD appropriations proposed in the Amending Letter.

The European Parliament adopted the 2010 budget in its plenary session of December 2009.

The voted EAFRD budget amounted to EUR 14 358 million in commitment appropriations and EUR 12 615 million in payment appropriations.

| Budget Item | Commitment appropriations (in €) | Payment appropriations (in €) |
| --- | --- | --- |
| 05.040501 (Rural dev. Programmes) | 14 335 536 182 | 12 606 200 000 |
| 05.040502 (Technical assistance) | 22 548 451 | 9 000 000 |

# Management of appropriations

## Management of Commitment appropriations

### EAFRD operational programmes

In 2010 the available commitment appropriations amounted in total to EUR 14.59 billion. Of this amount, EUR 14.34 billion corresponded to the approved budget and EUR 252 million were appropriations carried over from 2009. The carryover decision, adopted in February 2010, concerned part of the EERP appropriations that could not be committed in 2009 due to the late submission of some revised rural development programmes from the Member States.

The total amount of appropriaitons available  for EAFRD programmes in 2010 was committed (EUR 14.59 billion).

| Management of commitment appropriations in 2010 – EAFRD | Budget Item 05.040501 (amounts in €) |
| --- | --- |
| Appropriations at the beginning of 2010 | 14 335 536 182 |
| Carry-over from 2009 | 252 029 757 |
| Appropriations available in 2010 | 14 587 656 939 |
| Appropriations used in 2010 | 14 587 565 939 |

### Technical assistance

Article 69, 2nd paragraph of Council regulation (EC) No 1698/2005 stipulates that 0.25% of the resources for Community support to rural development shall be devoted to technical assistance for the Commission. In the 2010 budget, the amount available for this purpose was EUR 22.5 million. At the end of 2010, the total amount committed was EUR 4.9 million.

## Management of payment appropriations

### EAFRD operational programmes

In 2010 the initial payment appropriations amounted to EUR 12.6 billion. In view of the revised payment forecast submitted by the Member States in September 2010, the appropriations were reduced by EUR 1 160 million through the global transfer procedure. Once the Member States submitted their declarations of expenditure for the third quarter, an additional surplus of EUR 330 million was identified and proposed for reduction in a Draft Amending Budget. However, as this Amending Budget was finally not adopted, those payment appropriations remained unused at the end of the year. The unused amount reflects the fact that declarations of expenditure for the third quarter were slightly below the revised forecasts; and the fact that part of the payment requests for the third quarter submitted by several Member States could not be reimbursed because of the exhaustion of the available commitment appropriations. The unused appropriations were carried over to 2011.

The total amount paid to Member States for EAFRD programmes in 2010 reached EUR 11.1 billion.

| Management of payment appropriations in 2010 – EAFRD | Budget Item 05.040501 (amounts in €) |
| --- | --- |
| Appropriations at the beginning of 2010 | 12 606 200 000 |
| Global transfer | -1 160 000 000 |
| Appropriations available in 2010 | 11 446 200 000 |
| Appropriations used in 2010 | 11 116 180 326 |
| Unused amounts and carry over at the end of 2010 | 330 019 674 |

### Technical assistance

In the 2010 budget, the amount for payment appropriations was EUR 9 million. This amount was reduced by EUR 2.5 million through the global transfer. At the end of the year, the total amount of payments was EUR 4.4 million, leaving EUR 2.1 million unused.

# implementation of the 2010 EAFRD budget

## Introduction

Financial year 2010 mostly represented a consolidation period where many rural development programmes attained their cruising speed. However, this was an uneven situation as several programmes showed significant implementation difficulties because of the economic and financial crisis which had an effect on the Member States' ability to provide the national co-financing and might have caused beneficiaries to hesitate to enter into any commitments; the late approval of certain programmes; and the lack of sufficient previous experience of some Member States in the implementation of Rural Development programmes.

## Implementation of commitment appropriations

### EAFRD operational programmes

The table below shows the amounts committed per Member State in 2010 and the allocation established by Commission decision 2006/636/EC (modification of April 2010 still in force at the end of the year).

In 2010, the commitment appropriations available for EAFRD programmes amounted to EUR 14.59 billion. This amount included EUR 14.34 billion corresponding to the 2010 allocation as established in Decision 2006/636/EC and EUR 252 million carried over from 2009. All the available appropriations were committed during the year (EUR 14.34 billion).

| Commission Decision 2006/636/EC (last version in force end of 2009) vs. the amounts committed end of 2010: |  |  |  |
| --- | --- | --- | --- |
| Budget item: 05.040501 |  |  | (in €) |
| MS | Commission Decision 2006/636/EC – EU funds 2010 | Amounts carried over for commitment in 2010 | Amounts committed in the budget year 2010 |
|  | (a) | (b) | (c=a+b) |
| AT | 586 983 505 | 0 | 586 983 505 |
| BE | 70 637 509 | 1 110 000 | 71 747 509 |
| BG | 412 748 664 | 19 500 000 | 432 248 664 |
| CY | 23 911 507 | 0 | 23 911 507 |
| CZ | 415 632 774 | 21 000 000 | 436 632 774 |
| DE | 1 311 256 553 | 14 229 104 | 1 325 485 657 |
| DK | 85 052 762 | 0 | 85 052 762 |
| EE | 104 667 353 | 0 | 104 667 353 |
| ES | 1 400 090 047 | 49 871 207 | 1 449 961 254 |
| FI | 313 973 134 | 126 846 | 314 099 980 |
| FR | 1 091 752 155 | 165 200 | 1 091 917 355 |
| GR | 492 922 509 | 28 720 000 | 521 642 509 |
| HU | 529 160 494 | 28 440 000 | 557 600 494 |
| IE | 363 518 252 | 17 680 000 | 381 198 252 |
| IT | 1 256 577 236 | 38 596 000 | 1 295 173 236 |
| LT | 253 855 536 | 0 | 253 855 536 |
| LU | 13 838 190 | 0 | 13 838 190 |
| LV | 153 226 381 | 0 | 153 226 381 |
| MT | 10 964 212 | 0 | 10 964 212 |
| NL | 87 111 293 | 0 | 87 111 293 |
| PL | 1 935 872 838 | 0 | 1 935 872 838 |
| PT | 592 619 895 | 0 | 592 619 895 |
| RO | 1 401 644 651 | 0 | 1 401 644 651 |
| SE | 280 491 463 | 13 820 000 | 294 311 463 |
| SI | 134 100 946 | 0 | 134 100 946 |
| SK | 266 600 239 | 14 700 000 | 281 300 239 |
| UK | 746 326 084 | 4 071 400 | 750 397 484 |
| Total | 14 335 536 182 | 252 029 757 | 14 587 565 939 |

### Technical assistance

The table below shows the commitment appropriations for technical assistance consumed in 2010. The most important part is related to European Network for Rural Development.

| Technical assistance – Implementation of commitment appropriations |  |
| --- | --- |
| Budget Item: 05.040502 | (in €) |
| Description | Amount committed |
| Contact point of the European Network for Rural Development (ENRD) | 4 061 754 |
| Information technology | 219 730 |
| Thematic working groups ENRD | 350 754 |
| Experts committee on the evaluation of rural development programmes | 200 000 |
| Publications | 100 387 |
| Total | 4 932 625 |

## Implementation of payment appropriations

### EAFRD operational programmes

In the 2010 budget the amount for payment appropriations was 
EUR 12.61 billion. The global transfer reduced this amount by 
EUR -1.16 billion so that the appropriations of the year finally amounted to EUR 11.45 billion.

At the end of 2010, the total amount paid for EAFRD programmes was 
EUR 11.12 billion. The difference between the appropriations of the year 
(EUR 11.45 billion) and the total amount paid is EUR 330 million, which represents an under-execution of 2.88%. It should be noted that the payments made in 2010 increased more than 35% compared to 2009.

The table below shows the breakdown of payments made in 2010 by declaration period :

| Payments 2010 – EAFRD operational programmes million € |  |
| --- | --- |
| Reimbursement of payment claims Q3 2009 | 127.31 |
| Reimbursement of payment claims Q4 2009 | 2 947.20 |
| Reimbursement of payment claims Q1 2010 | 2 124.25 |
| Reimbursement of payment claims Q2 2010 | 2 073.00 |
| Reimbursement of payment claims Q3 2010 | 3 443.28 |
| Advances | 401.15 |
| Total 2010 | 11 116.18 |

The reimbursement of 3rd quarter 2010 for 5 EAFRD programmes was totally or partiality on hold at the end of the year because the outstanding commitment appropriations for these programmes were fully exhausted by the payment of previous claims. The table below shows the 5 EAFRD programmes and the corresponding amounts. The payment had to wait until the annual commitments for 2011 were made.

| EAFRD Programs– Nº CCI | Q3 2010 (in€) |
| --- | --- |
| Vlaanderen (2007BE06RPO001) | 6 655 665 |
| Bayern (2007DE06RPO004) | 29 517 043 |
| Ireland National (2007IE06RPO001) | 32 730 873 |
| Bolzano (2007IT06RPO002) | 990 232 |
| Luxembourg (2007LU06RPO001) | 262 045 |
| Total | 70 155 858 |

The monthly consumption of payment appropriations during the year (January to December 2010) is represented in the graph below. The rhythm of consumption is linked to the calendar for sending the four payment declarations (31 January, 30 April, 31 July and 10 November for the payment claims corresponding respectively to Q4 2009, Q1 2010, Q2 2010 and Q3 2010).

The breakdown per Member State and per declaration period of the amounts paid by the Commission in budget year 2010 is shown in the following table. The amounts from column Q3 2009 relate to the EAFRD programmes that exhausted their commitment appropriations for 2009 and had to wait until 2010 to have their amounts reimbursed with the 2010 commitment appropriations.

| Payments effectively made between 01/01/2010 and 31/12/2010 |  |  |  |  |  |  | (in €) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MS | Q3 2009 | Q4 2009 | Q1 2010 | Q2 2010 | Q3 2010 | Advances | Grand Total |
| AT |  | 455 569 614 | 43 672 108 | 44 906 450 | 37 674 070 | 7 987 420 | 589 809 662 |
| BE | 6 425 513 | 5 218 982 | 10 904 604 | 26 499 701 | 16 734 243 | 4 821 180 | 70 604 223 |
| BG |  | 10 833 902 | 99 737 836 | 109 667 733 | 55 280 536 | 2 320 500 | 277 840 508 |
| CY |  | 5 844 859 | 4 092 969 | 3 006 340 | 3 221 705 | 142 800 | 16 308 673 |
| CZ |  | 71 116 190 | 219 606 417 | 92 176 063 | 55 446 653 | 2 940 000 | 441 285 322 |
| DE | 10 634 843 | 449 653 563 | 137 650 080 | 90 433 394 | 374 027 292 | 67 702 460 | 1 130 101 633 |
| DK |  | 22 509 479 | 11 031 696 | 8 301 380 | 9 257 104 | 9 328 060 | 60 427 719 |
| EE |  | 11 014 279 | 52 150 110 | 12 978 492 | 16 374 090 | 635 460 | 93 152 431 |
| ES | 2 506 310 | 219 017 075 | 146 477 779 | 148 788 488 | 290 719 234 | 58 741 200 | 866 250 086 |
| FI | 98 743 | 79 327 737 | 13 676 425 | 12 679 542 | 181 220 600 | 5 256 020 | 292 259 068 |
| FR |  | 186 049 035 | 130 073 442 | 92 283 874 | 382 352 635 | 79 977 240 | 870 736 226 |
| GR |  | 39 973 082 | 12 150 331 | 119 315 280 | 233 200 744 | 13 924 680 | 418 564 116 |
| HU |  | 146 605 566 | 114 137 436 | 112 972 138 | 77 779 633 | 3 797 360 | 455 292 132 |
| IE | 107 643 643 | 87 587 253 | 55 583 262 | 38 086 416 | 81 473 859 | 10 823 820 | 381 198 252 |
| IT |  | 175 925 287 | 77 580 985 | 126 397 795 | 235 683 411 | 48 564 040 | 664 151 518 |
| LT |  | 60 891 489 | 73 440 397 | 56 368 010 | 49 387 045 | 1 570 380 | 241 657 321 |
| LU |  | 5 362 753 | 5 090 031 | 1 385 947 | 3 765 284 | 344 400 | 15 948 416 |
| LV |  | 33 969 622 | 45 596 012 | 25 735 665 | 51 538 859 | 928 200 | 157 768 358 |
| MT |  | 1 937 682 | 1 439 925 | 2 877 517 | 10 853 260 | 71 400 | 17 179 784 |
| NL |  | 17 739 157 | 17 108 137 | 13 801 790 | 16 761 310 | 7 467 320 | 72 877 714 |
| PL |  | 329 716 307 | 477 616 176 | 283 114 658 | 337 768 509 | 11 822 300 | 1 440 037 950 |
| PT |  | 43 519 546 | 33 409 884 | 137 575 894 | 232 644 503 | 9 078 860 | 456 228 687 |
| RO |  | 60 250 707 | 64 728 636 | 279 349 875 | 349 034 410 | 7 118 580 | 760 482 207 |
| SE |  | 114 003 289 | 37 089 368 | 21 201 521 | 112 977 181 | 8 918 980 | 294 190 338 |
| SI |  | 43 330 855 | 12 979 172 | 36 286 031 | 18 819 694 | 1 100 820 | 112 516 573 |
| SK |  | 154 336 375 | 75 990 280 | 72 653 554 | 72 766 745 | 1 924 300 | 377 671 253 |
| UK |  | 115 891 789 | 151 235 571 | 104 153 251 | 136 518 327 | 33 841 220 | 541 640 158 |
| Total | 127 309 052 | 2 947 195 476 | 2 124 249 066 | 2 072 996 797 | 3 443 280 935 | 401 149 000 | 11 116 180 326 |

Of the total amount paid in 2010 EUR 10.72 billion, relates to reimbursements and EUR 401 million to advances.

The table in the next page compares, for each Member State, the EAFRD payments made in 2010 with the payments in 2009. While interim payments in 2010 increased by 30.5% compared to 2009 (EUR 10.72 billion vs. 8.21 billion), total payments increased by 35.4% (EUR 11.12 billion vs. 8.21 billion) due to the impact of the supplementary advances paid during the year

| Payments made to Member States - Comparison 2010 vs 2009 |  |  |  |  |  |  | (in €) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MS | 2009 |  |  | 2010 |  |  | Difference 2010 vs. 2009 |  |
|  | Interim payments | Prefinancing | Total | Interim payments | Prefinancing | Total | ( in €) | ( in %) |
| AT | 550 352 330 |  | 550 352 330 | 581 822 242 | 7 987 420 | 589 809 662 | 39 457 332 | 7.2% |
| BE | 57 909 148 |  | 57 909 148 | 65 783 043 | 4 821 180 | 70 604 223 | 12 695 075 | 21.9% |
| BG | 127 052 991 |  | 127 052 991 | 275 520 008 | 2 320 500 | 277 840 508 | 150 787 517 | 118.7% |
| CY | 16 161 768 |  | 16 161 768 | 16 165 873 | 142 800 | 16 308 673 | 146 904 | 0.9% |
| CZ | 340 175 929 |  | 340 175 929 | 438 345 322 | 2 940 000 | 441 285 322 | 101 109 393 | 29.7% |
| DE | 930 186 410 |  | 930 186 410 | 1 062 399 173 | 67 702 460 | 1 130 101 633 | 199 915 223 | 21.5% |
| DK | 53 861 495 |  | 53 861 495 | 51 099 659 | 9 328 060 | 60 427 719 | 6 566 224 | 12.2% |
| EE | 95 121 150 |  | 95 121 150 | 92 516 971 | 635 460 | 93 152 431 | -1 968 719 | -2.1% |
| ES | 618 592 973 |  | 618 592 973 | 807 508 885 | 58 741 200 | 866 250 086 | 247 657 113 | 40.0% |
| FI | 191 126 077 |  | 191 126 077 | 287 003 048 | 5 256 020 | 292 259 068 | 101 132 991 | 52.9% |
| FR | 779 806 772 |  | 779 806 772 | 790 758 986 | 79 977 240 | 870 736 226 | 90 929 454 | 11.7% |
| GR | 174 132 448 |  | 174 132 448 | 404 639 436 | 13 924 680 | 418 564 116 | 244 431 667 | 140.4% |
| HU | 497 184 388 |  | 497 184 388 | 451 494 772 | 3 797 360 | 455 292 132 | -41 892 256 | -8.4% |
| IE | 329 171 422 |  | 329 171 422 | 370 374 432 | 10 823 820 | 381 198 252 | 52 026 830 | 15.8% |
| IT | 356 692 296 |  | 356 692 296 | 615 587 478 | 48 564 040 | 664 151 518 | 307 459 221 | 86.2% |
| LT | 247 493 642 |  | 247 493 642 | 240 086 941 | 1 570 380 | 241 657 321 | -5 836 321 | -2.4% |
| LU | 12 910 511 |  | 12 910 511 | 15 604 016 | 344 400 | 15 948 416 | 3 037 905 | 23.5% |
| LV | 104 463 393 |  | 104 463 393 | 156 840 158 | 928 200 | 157 768 358 | 53 304 965 | 51.0% |
| MT | 3 357 534 |  | 3 357 534 | 17 108 384 | 71 400 | 17 179 784 | 13 822 250 | 411.7% |
| NL | 36 071 974 |  | 36 071 974 | 65 410 394 | 7 467 320 | 72 877 714 | 36 805 741 | 102.0% |
| PL | 1 043 825 682 |  | 1 043 825 682 | 1 428 215 650 | 11 822 300 | 1 440 037 950 | 396 212 268 | 38.0% |
| PT | 235 563 950 |  | 235 563 950 | 447 149 827 | 9 078 860 | 456 228 687 | 220 664 737 | 93.7% |
| RO | 565 927 879 |  | 565 927 879 | 753 363 627 | 7 118 580 | 760 482 207 | 194 554 328 | 34.4% |
| SE | 105 868 407 |  | 105 868 407 | 285 271 358 | 8 918 980 | 294 190 338 | 188 321 932 | 177.9% |
| SI | 100 732 462 |  | 100 732 462 | 111 415 753 | 1 100 820 | 112 516 573 | 11 784 110 | 11.7% |
| SK | 289 286 329 |  | 289 286 329 | 375 746 953 | 1 924 300 | 377 671 253 | 88 384 924 | 30.6% |
| UK | 346 343 895 |  | 346 343 895 | 507 798 938 | 33 841 220 | 541 640 158 | 195 296 263 | 56.4% |
| Total | 8 209 373 256 | 0.00 | 8 209 373 256 | 10 715 031 326 | 401 149 000 | 11 116 180 326 | 2 906 807 070 | 35.4% |

### Technical assistance

In the 2010 budget the amount for payment appropriations was € 9 million. The table hereafter presents the payments for technical assistance for a total amount of EUR 4.4 million. The most important part is related to European Network for Rural Development.

| Technical assistance – Implementation of payment appropriations |  |
| --- | --- |
| Budget Item: 05.040502 | (in €) |
| Description | Amount paid |
| Seminar on the implementation of rural development programmes | 107 687 |
| Contact point of the European Network for Rural Development (ENRD) | 3 928 213 |
| Thematic working groups ENRD | 205 202 |
| Experts committee on the evaluation of rural development programmes | 76 784 |
| Publications | 88 516 |
| Total | 4 406 402 |

## Analysis of expenditure declared by axis and by measure

The table below shows the payment claims declared by Member state and by axis/measure for rural development in 2010 (Q4 2009 to Q3 2010), the cumulative declared expenditure from 2007 to 2010 (Q4 2006 to Q3 2010) and also the financial plans of EAFRD programmes (2007-2013; EU27).

In 2010, the expenditure continues to be concentrated in axis 2 (50.9%), followed by axis 1 with  35.4%, axis 3 with  9.10% and axis 4 with  2.5%. This repartition of expenditure still significantly diverges with the repartition in the financial plans for the 2007-2013 programming period (33.6%, 44.4%, 13.3% and  6% for axis 1 to 4 respectively).

Axis 2 measures mainly involve annual payments (e.g. agro-environmental measures) whilst Axis 1, 3 and, to a lesser extent, Axis 4 mainly relate to multi-annual measures that require longer proceedings for their approval and implementation (e.g. investment projects)..

Compared with the average for the first 3 years (2007-2009), the expenditure in  2010 is more balanced among axes and the share of each axis tends to get closer to the share in the financial plans. For instance, Axis 2 decreases from  57.8% in 2009 to  50.0% in 2010 while Axis 1 increases from 32.0% in 2009 to  35.4% in 2010.

| EAFRD declared expenditure 2010 (Q4 2009-Q3 2010) & Total cumulative expenditure (Q4 2006 to Q3 2010) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| compared with Financial Plans |  |  |  |  |  |  |
|  | Declared expenditure 2010 (Q4 2009 to Q3 2010) |  | Cumulative declared expenditure (Q4 2006 to Q3 2010) |  | Financial Plans 2007-2013 |  |
| EAFRD Axis / Measure | (million €) | (%) | (million €) | (%) | (million €) | (%) |
| 111 Vocational training and information actions | 78.9 | 0.7% | 156.5 | 0.6% | 1 089.2 | 1.1% |
| 112 Setting up of young farmers | 345.9 | 3.2% | 838.1 | 3.1% | 2 887.5 | 3.0% |
| 113 Early retirement | 351.7 | 3.3% | 1 040.1 | 3.8% | 2 853.0 | 3.0% |
| 114 Use of advisory services | 11.0 | 0.1% | 19.7 | 0.1% | 440.1 | 0.5% |
| 115 Setting up of management, relief and advisory | 2.5 | 0.0% | 4.0 | 0.0% | 93.5 | 0.1% |
| 121 Modernisation of agricultural holdings | 1 728.3 | 16.2% | 3 537.9 | 12.9% | 10 667.0 | 11.1% |
| 122 Improvement of the economic value of forest | 32.5 | 0.3% | 80.1 | 0.3% | 653.7 | 0.7% |
| 123 Adding value to agricultural and forestry | 585.3 | 5.5% | 1 016.0 | 3.7% | 5 647.3 | 5.9% |
| 124 Cooperation for development of new products | 12.4 | 0.1% | 18.0 | 0.1% | 349.3 | 0.4% |
| 125 Infrastructure related to the development … | 406.3 | 3.8% | 753.9 | 2.7% | 5 129.4 | 5.3% |
| 126 Restoring agricultural production potential | 49.1 | 0.5% | 104.9 | 0.4% | 477.5 | 0.5% |
| 131 Meeting standards based on Community... | 2.9 | 0.0% | 45.0 | 0.2% | 103.9 | 0.1% |
| 132 Participation of farmers in food quality … | 9.5 | 0.1% | 16.5 | 0.1% | 294.1 | 0.3% |
| 133 Information and promotion activities | 8.0 | 0.1% | 12.9 | 0.0% | 206.4 | 0.2% |
| 141 Semi-subsistence farming | 130.9 | 1.2% | 391.0 | 1.4% | 993.9 | 1.0% |
| 142 Producer groups | 23.2 | 0.2% | 56.2 | 0.2% | 327.9 | 0.3% |
| 143 Direct Payment (BG + RO) | 1.1 | 0.0% | 1.7 | 0.0% | 131.8 | 0.1% |
| 144 Holdings undergoing restructuring | - | 0.0% | - | 0.0% | 17.0 | 0.0% |
| Axis 1 | 3 779.3 | 35.4% | 8 092.6 | 29.5% | 32 362.5 | 33.6% |
| 211 Natural handicap payments to farmers in ... | 1 003.8 | 9.4% | 3 163.9 | 11.5% | 6 240.9 | 6.5% |
| 212 Payments to farmers in areas with handicaps... | 1 026.7 | 9.6% | 3 269.3 | 11.9% | 7 241.4 | 7.5% |
| 213 Natura 2000 payments and payments linked.. | 23.0 | 0.2% | 55.7 | 0.2% | 476.7 | 0.5% |
| 214 Agri-environment payments | 2 897.4 | 27.1% | 8 960.3 | 32.6% | 22 231.3 | 23.1% |
| 215 Animal welfare payments | 62.4 | 0.6% | 143.1 | 0.5% | 543.0 | 0.6% |
| 216 Non-productive investments | 34.6 | 0.3% | 54.7 | 0.2% | 591.1 | 0.6% |
| 221 First afforestation of agricultural land | 179.9 | 1.7% | 636.6 | 2.3% | 2 295.0 | 2.4% |
| 222 First establishment of agroforestry systems .... | - | 0.0% | - | 0.0% | 16.4 | 0.0% |
| 223 First afforestation of non-agricultural land | 18.9 | 0.2% | 37.2 | 0.1% | 347.8 | 0.4% |
| 224 Natura 2000 payments | 3.7 | 0.0% | 7.0 | 0.0% | 102.0 | 0.1% |
| 225 Forest-environment payments | 4.9 | 0.0% | 13.1 | 0.0% | 271.4 | 0.3% |
| 226 Restoring forestry potential and … | 132.4 | 1.2% | 323.6 | 1.2% | 1 609.7 | 1.7% |
| 227 Non-productive investments | 49.4 | 0.5% | 113.5 | 0.4% | 808.9 | 0.8% |
| Axis 2 | 5 437.2 | 50.9% | 16 778.0 | 61.1% | 42 775.5 | 44.4% |
| 311 Diversification into non-agricultural activities | 100.1 | 0.9% | 165.2 | 0.6% | 1 488.9 | 1.5% |
| 312 Business creation and development | 107.2 | 1.0% | 149.8 | 0.5% | 2 208.8 | 2.3% |
| 313 Encouragement of tourism activities | 78.6 | 0.7% | 127.5 | 0.5% | 1 291.0 | 1.3% |
| 321 Basic services for the economy and rural … | 219.9 | 2.1% | 320.4 | 1.2% | 3 120.2 | 3.2% |
| 322 Village renewal and development | 330.0 | 3.1% | 487.3 | 1.8% | 3 107.9 | 3.2% |
| 323 Conservation and upgrading of the rural ... | 104.7 | 1.0% | 194.8 | 0.7% | 1 314.6 | 1.4% |
| 331 Training and information | 9.6 | 0.1% | 16.9 | 0.1% | 147.5 | 0.2% |
| 341 Skills acquisition, animation and implementation | 17.4 | 0.2% | 35.2 | 0.1% | 150.0 | 0.2% |
| Axis 3 | 967.4 | 9.1% | 1 497.2 | 5.5% | 12 829.0 | 13.3% |
| 411 Implementing local development strategies... | 16.8 | 0.2% | 26.4 | 0.1% | 471.9 | 0.5% |
| 412 Implementing local development strategies... | 1.5 | 0.0% | 2.3 | 0.0% | 167.0 | 0.2% |
| 413 Implementing local development strategies.... | 155.5 | 1.5% | 212.5 | 0.8% | 3 877.5 | 4.0% |
| 421 Implementing cooperation projects | 2.6 | 0.0% | 3.3 | 0.0% | 278.6 | 0.3% |
| 431 Running the local action group, acquiring... | 93.3 | 0.9% | 121.5 | 0.4% | 959.8 | 1.0% |
| Axis 4 | 269.8 | 2.5% | 366.0 | 1.3% | 5 754.7 | 6.0% |
| 511 Technical Assistance | 124.6 | 1.2% | 288.0 | 1.0% | 1 876.9 | 2.0% |
| 611 BG RO Direct Payments | 98.7 | 0.9% | 438.2 | 1.6% | 645.6 | 0.7% |
| Grand total | 10 677.0 | 100.0% | 27 460.0 | 100.0% | 96 244.2 | 100.0% |

## Implementation of EAFRD programmes

The graph on the next page presents the financial implementation rate of rural development programmes (from the beginning to 2010, including Q4 2010) compared with the 2007-2010 appropriations. The average EAFRD financial implementation rate for all EAFRD programmes is 72.4%.

The graph shows that most Member States have absorbed more than 60% of the 2007-2010 appropriations.

.