Scaling-up of funding under the Facility for Refugees in Turkey following the EU-Turkey Statement

| Funding Strand under the Fast-Track Approach | Humanitarian Assistance | Special Measure on Support to Returned Migrants | Special Measure of July 2016 Education & Health | Special Measure of July 2016 Infrastructure & Socio-Economic Support | EU Regional Trust Fund in Response to the Syrian Crisis (EUTF) |
| --- | --- | --- | --- | --- | --- |
| Next steps | Since October Roll-out of the Emergency Social Safety Net (ESSN) - started in October 2016 to reach as many as 1 million vulnerable refugees in 2017. | Since August Implementation of the Special Measure on support to returned migrants | Since October Implementation of the direct grants for education and health of EUR 300 million each | Since August Preparation of the remaining delegation agreements with International Financial Institutions (IFIs) | End of December Two contracts are foreseen to be signed. The first, worth EUR 33 million, will involve the Danish Red Cross and the Turkish Red Crescent. The second, worth EUR 5 million, will be implemented by Spark, a Dutch NGO, in the area of higher education of vulnerable Syrian youth. Since June Preparation of projects in areas not covered by other strands: labour market access, community actions, smaller grant initiatives, other integration and soft measures. |
| Achievements | Early September Signature of the ESSN contract for a value of EUR 348 million. 31 July Signature of EUR 74 million in the field of health, education, protection and winterisation. 3 June Publication of the Commission's Humanitarian Implementation Plan including the first allocation (EUR 505.65 million) March/April The Commission signs projects with 17 humanitarian partners worth EUR 90 million. | 8 August Direct agreement to implement the Special Measure on support to returned migrants signed by the Turkish authorities on 8 August 2016. Advance of EUR 12 million paid on 18 August 2016. 19 April The Special Measure of EUR 60 million committed to provide food, shelter and health care for returned migrants from Greece. | October Payment of the advances worth EUR 270 million End September Signature of the direct grants for education and health of EUR 300 million each. | 28 November Signature of a contract worth EUR 50 million with KfW to build and furnish new schools. |  |
|  |  |  | 28 July Adoption of EUR 1.4 billion Special Measure on education, health, municipal infrastructure and socio-economic support including a top up of EUR 250 million for EUTF funded bottom-up projects. |  |  |
|  |  |  |  | June IFIs roundtables on 24 and 29 June discussed and endorsed the Special Measure | June An additional four bottom-up projects for a total EUR 59 million adopted by the EUTF Board in April and June to provide additional education support and infrastructure, higher education, skills training, social support. May Four projects contracted for a total EUR 60 million, including the UNICEF regional contract with EUR 37 million component for Turkey signed on 4 March. |
| Facility Governance |  |  |  |  |  |
| Timeline since April: | April Fast-track approach presented to Turkey and further elaborated to become Strategic Concept Note for the implementation of the Facility. | 12 May 2nd Steering Committee endorsed Strategic Concept Note and received a presentation of the independent needs assessment. It agreed on six Facility priority areas: humanitarian assistance, migration management, education, health, municipal infrastructure, and socio-economic support. | 13 June All Member States' contribution certificates received, covering full amount of EUR 2 billion pledged for 2016-2017. | 30 June 3rd Steering Committee reviewed implementation and discussed Special Measures on education, health, municipal and social infrastructure, and socio-economic support, prior to IPA Management approval of the Measure in July. | 4 October 4th Steering Committee Continuous Reporting on implementation and communicating on results achieved including with interactive map. 12 January 2017 5th Steering Committee |

For further information on how the facility works and a detailed overview of projects funded: http://ec.europa.eu/enlargement/news_corner/migration/index_en.htm