**Annex 1**

**Composition of Expert Groups and number of meetings held during the implementation period of the second EU Work Plan for Sport (2014 – 2017)**

|  |  |  |  |
| --- | --- | --- | --- |
| **Expert Group** | **Member States** | **Observers** | **No. of meetings** |
| Match-fixing | 24 | 24 | 5 |
| Good Governance | 24 | 26 | 7 |
| Economic Dimension | 25 | 24 | 4 |
| HEPA | 28 | 17 | 5 |
| Human Resources Development in Sport | 26 | 15 | 7 |

**Annex 2**

**Status of delivered outputs under the second EU Work Plan for Sport (2014 – 2017)**

**(by October 2016)**

|  | **Output** | **Working Structure in Charge** | **Target Date** | **Status** | **Presentation to the Working Party on Sport (WPS)** |
| --- | --- | --- | --- | --- | --- |
| 1 | Exchange of best practices and peer learning based on the Expert Group recommendations on prevention of doping in recreational sport (delivered during the first Work Plan for Sport)  | Directors General for Sport | 2nd half 2015 | Completed | Presented to WPS on 09/04/2015 |
| 2 | Exchange of best practices regarding the fight against match-fixing, in particular on a possible Commission Recommendation on best practices in the prevention and combatting of betting-related match-fixing, followed by a report on state of play | Expert Group on Match Fixing | 1st half 2016 | Completed | Presented to WPS on 05/12/2016 |
| 3 | Preparation of Expert Group recommendations to protect young athletes and safeguard children's rights in sport | Expert Group on Good Governance | 1st half 2016 | Completed | Presented to WPS on 02/09/2016 |
| 4 | Preparation of guiding principles relating to democracy, human rights and labour rights, in particular in the context of the awarding procedure of major sport events, possibly followed by a pledge board. | Expert Group on Good Governance | 2nd half 2015 | Completed | Presented to WPS on 15/01/2016 |
| 5 | Promotion of existing good governance principles, possibly followed by a pledge board | Expert Group on Good Governance | 2nd half 2015 | Completed | Presented to WPS on 02/09/2016 |
| 6 | Preparation of Expert Group recommendations or guidelines on gender equality in sport, possibly followed by a pledge board | Expert Group on Good Governance | 2nd half 2015 | Completed | Presented to WPS on 15/02/2016 |
| 7 | Preparation of Expert Group recommendations to measure the economic benefits of sport in the EU based on the ongoing work to promote the set-up of SSAs in the Member States | Expert Group on Economic Dimension | 2nd half 2015 | Completed | Presented to WPS on 25/04/2016 |
| 8 | Preparation of Expert Group recommendations on major sport events, in particular on legacy aspects with a focus on social, economic and environmental sustainability | Expert Group on Economic Dimension | 2nd half 2015 | Completed | Presented to WPS on 15/01/2016 |
| 9 | Preparation of practical guidance on how to encourage transparent and long-term investment in sport, including EU funding, based inter alia on 2012 recommendations on sustainable financing of sport, including state aid | Expert Group on Economic Dimension | 1st half 2016 | Completed | Presented to WPS on 24/10/2016 |
| 10 | Preparation of Expert Group recommendations to encourage physical education in schools, including motor skills in early childhood, and to create valuable interactions with the sport sector, local authorities and the private sector | Expert Group on HEPA | 1st half 2015 | Completed | Presented to WPS on 06/07/2015 |
| 11 | Coordination of the implementation of the Council Recommendation on HEPA | Expert Group on HEPA | 2nd half 2016 | Completed | Presented to WPS on 24/10/2016 |
| 12 | Preparation of Expert Group recommendations to encourage volunteering in sport, including best practices on legal and fiscal mechanisms | Expert Group Human Resources Development in Sport | 2nd half 2015 | Completed | Presented to WPS on 04/11/2016 |
| 13 | Exchange of best practices and report on the state of play concerning the inclusion of sport qualifications in NQFs with a reference to EQF | Expert Group Human Resources Development in Sport | 2nd half 2016 | In progress | To be presented to the WPS |
| 14 | Preparation of Expert Group recommendations on the contribution of sport to the employability of young people, including young professional sportsmen and women, and the creation of jobs in the sport and sport-related labour market | Expert Group Human Resources Development in Sport | 2nd half 2016 | In progress | To be presented to the WPS |
| 15 | Preparation of practical guidance on compliance of national qualifications with international qualification standards of international sport federation | Expert Group Human Resources Development in Sport | 2nd half 2015 | Completed | Presented to WPS on 05/12/2016 |
| 16 | Preparation of a report on state of play concerning the implementation of the EU Guidelines on Dual Careers | Expert Group Human Resources Development in Sport | 1st half 2017 | In progress | To be presented to the WPS |