

1. **The evaluation and the need for an EU Action Plan on drugs for 2017-2020**

The EU's Drugs Strategy 2013-2020[[1]](#footnote-1) and its first Action Plan on Drugs 2013-2016[[2]](#footnote-2) set out a political framework and priorities for the EU’s drugs policy. The Strategy provides a single, evidence-based framework for tackling drugs inside and outside the EU, and is based on a five pillar structure consisting of:

* two main policy areas
  + the reduction of the drug demand and
  + the reduction of drug supply;
* and three cross-cutting themes:
  + coordination,
  + international cooperation and
  + research, information, monitoring and evaluation.

The Strategy requires the Commission to *"initiate an external midterm assessment of the Strategy by 2016, in view of preparing a second Action Plan for the period 2017-2020"*. The European Agenda on Security[[3]](#footnote-3) provides for the Commission to assess progress in implementing the 2013-2016 Action Plan and decide on that basis whether to propose a new Action Plan for 2017-2020.

With the support of an external contractor[[4]](#footnote-4), the Commission conducted the mid-term assessment of the Strategy and the final evaluation of the Action Plan between April and November 2016[[5]](#footnote-5). Due to their complementarity and interconnection, these are presented in the form of a single, comprehensive evaluation.

This Communication sets out the results of the evaluation[[6]](#footnote-6) and proposes the steps to be taken next. In view of the overall findings of the evaluation, the Commission has decided to propose a new Action Plan for the period 2017-2020. Building on the results of the evaluation, and given that the strategic framework will not change before 2020, the new proposed Action Plan is an updated version of the EU Action Plan on Drugs 2013-2016 with a number of modifications. It reflects the findings and the recommendations of the assessment that the Commission found pertinent as well as a number of additional actions to address new and emerging priorities which have not been sufficiently covered by the previous Action Plan, but are relevant in light of challenges EU Member States are currently facing. The Commission's proposed draft Action Plan on drugs for 2017-2020 is set out in the annex below[[7]](#footnote-7).

1. **Context**

The market for illicit drugs is the most dynamic criminal market, as confirmed also in the European Agenda on Security. It is estimated that EU citizens spend over EUR 24 billion every year on illicit drugs[[8]](#footnote-8). The human and social costs of drugs addiction are very high and it generates costs for public health (drug prevention, healthcare and treatment), public safety, the environment and labour productivity[[9]](#footnote-9).

As regards drug demand, the use of illicit drugs remains one of the most longstanding threats to our societies and, whether directly or indirectly, affects the lives of millions of people. At least 83.2 million Europeans have reported that they have used cannabis at least once in their lifetime, while 17.1 and 12 million respectively have tried cocaine and amphetamines. In addition, 1.3 million adults are high-risk opioid users. The prevalence of recorded high-risk opioid use has stabilised and in some countries diminished; the prevalence of infectious diseases has been decreasing, overall, since 2013. It is estimated that at least 6 800 people died from overdoses in the EU in 2014[[10]](#footnote-10). Drug use is largely concentrated among young people (15 to 34 years old); an estimated 17.8 million young adults have used drugs in the last year. There appears to have been an increase in drug-related deaths since 2013 and no recorded decrease in the use of drugs.[[11]](#footnote-11)

As regards drug supply, in the past four years, new psychoactive substances (NPSs) have been increasingly available on the open market and/or online, posing serious health threats. In 2015, a total of 98 NPSs were detected, bringing the number of new substances monitored to more than 560, of which 70 % have been detected in the last five years. Recorded seizures of illicit drugs did not changed substantially in 2013 and 2014 compared with the previous year, but a greater total volume of drugs was seized.

As regards coordination, the mechanisms at EU level, most of which pre-date the current Strategy, are effective. Its most prominent coordination body, the EU Council's Horizontal Drugs Group (HDG), is considered effective in monitoring the implementation of the Action Plan and facilitating dialogue on the state of the drugs phenomenon in Europe. There is evidence of consistency over time and continuity across presidencies. In addition, all Member States reported that civil society organisations were involved in the development, monitoring and/or evaluation of their national drugs policy.

As regards international cooperation, drug-related priorities have been incorporated into the EU’s external policies, strategies and actions targeting third countries and regions. In addition, the past years have been an improvement in EU cooperation in order to speak as one voice in international fora.

Finally, regarding information, research, monitoring and evaluation over the last five years the EU has provided support to several research projects under a variety of funding mechanisms[[12]](#footnote-12) spanning various aspects of the drug issue and related disciplines. Sustained efforts are needed to translate the priorities of the Strategy and Action Plan in research. The existence and operation of the Early Warning System for new psychoactive substances within the European Monitoring Centre for Drugs and Drug Addiction (EMCDDA) is a reflection of improved sharing of forensic and toxicological data at EU level over the past years. This early warning activity allows the EU to make informed and swift decisions on harmful substances.

1. **Findings of the mid-term assessment of the Strategy and the final evaluation of the 2013-2016 Action Plan**

The evaluation covered the period 2013-2016 and all 28 Member States. It addressed both the internal and the external dimensions of the Strategy and the Action Plan. It was based on an extensive review of relevant EU and Member State data and documents relating to drug markets, trends and drugs strategies[[13]](#footnote-13). The findings of the evaluation addressed both the mid-term assessment of the EU Drugs Strategy 2013-2020 and the final evaluation of the EU Action Plan on Drugs 2013-2016.


Some of the main challenges of the evaluation were the fact that the data collected from all Member States to feed into it were not always comparable, as well as a lack of baseline measures and up to date statistics for certain areas[[14]](#footnote-14). This makes the attribution and assessment of possible trends and developments to the Strategy and the Action Plan difficult, which has had an impact on the analysis of the effectiveness of the Strategy and Action Plan in terms of quantifying the effects and crediting changes corresponding to the objectives solely to the Strategy and Action Plan. However, several research methods[[15]](#footnote-15) have been used for the evaluation and the findings from each data source have been combined, which contributed to the weight of evidence.

The evaluation concluded that the Strategy and Action Plan are still fit for purpose in terms of meeting the requirements of drugs policy at EU, national and international levels. All areas they tackle remain relevant for addressing all aspects of the drugs phenomenon.

The evaluation applied the five standard criteria: effectiveness, efficiency, coherence, relevance and EU added value.

* 1. **Effectiveness**

As a first step to assess effectiveness, the evaluation assessed the degree of implementation of all the 54 actions of the Action Plan, as well as their impact. The graph below shows the progress made in the Action Plan for each of the five pillars:

****

The evaluation found that implementation of the EU Drugs Strategy and Action Plan has been effective, to different degrees, in all five pillars.

The majority of the actions have been implemented - 53% of actions are completed or on track, whilst for 47% of actions some progress has been made but implementation is behind plan - and considerable progress has been made on the 15 specific objectives of the Action Plan.

In the area of drug demand reduction, delays relate to the objectives on preventing drug use and delaying the onset of drug use and on enhancing the effectiveness of drug treatment and rehabilitation. The objective of embed coordinated, best practice and quality approaches in drug demand reduction is on track.

In the area of drug supply reduction, the objectives to enhance effective law enforcement coordination and cooperation and enhancing effective judicial cooperation and legislation are behind schedule, whilst that related to responding effectively to current and emerging trends in illicit drug activity was assessed as on target.

In the area of coordination, the objectives relating to ensuring effective coordination at EU and national-level of drug-related policies and ensuring the participation of civil society in the formulation of drugs policy were assessed as on target.

In the field of international relations, the objective of integrating the Strategy into the EU's overall foreign policy framework was assessed as lagging behind, whilst objectives are on track relating to improving the cohesiveness of the EU’s approach and visibility in the United Nations (UN) and of supporting the process for acceding, candidate and potential candidates countries’ to adapt to and align with the EU acquis on drugs.

In the field of information, research, monitoring and evaluation, further progress is needed to ensure adequate investment in research, data collection, monitoring, evaluation and information exchange and to enhance the dissemination of monitoring, research and evaluation results at EU and national level. Progress on maintaining networking and cooperation and developing capacity within and across the EU’s knowledge infrastructure for information, research, monitoring and evaluation of drugs, particularly on illicit drugs was good.

* 1. **Efficiency**

In the absence of a comprehensive, up-to-date overview of drug-related expenditure, the evaluation provided indications of the extent to which sufficient financial resources had been allocated at EU and Member State level.

The evaluation could not conclude on the efficiency of the intervention as harmonised quantitative data are not available as regards expenditure and related benefits of relevant actions across EU Member States. However, the Drugs Strategy and Action Plan managed to establish a common EU-wide framework as explained in the "EU added value" section below. In the absence of a comprehensive and up-to-date overview of drug-related expenditure, the evaluation focussed instead on the extent to which the allocation of financial resources at EU and Member State level was perceived as sufficient. Overall, resources were considered by stakeholders to be sufficient for the EU Strategy and Action Plan, in particular with regard to drug demand and supply.

* 1. **Coherence**

The priorities and actions in the Strategy and Action Plan were found to be coherent with most other relevant EU policies and strategies, such as the European Agenda on Security and the European Development Consensus[[16]](#footnote-16), while more synergies with the EU Health Strategy[[17]](#footnote-17) are called for. For example, the evaluation points to the fact that the challenges posed by the ageing of the population in Europe or the potential impact of new technologies in the prevention area as identified in the EU Health Strategy are not reflected.

* 1. **Relevance**

According to the evaluation, stakeholders considered the Strategy and Action Plan to be as relevant as at the time of their adoption. The five pillar structure continues to address most current drugs policy requirements at EU and national level. All areas tackled in the Strategy and Action Plan 2013-2016 remain relevant for addressing all aspects of the drugs phenomenon.

* 1. **EU added value**

The Strategy and the Action Plan provided added value to individual Member States’ (and non-state actors) strategies by establishing a common EU-wide framework and institutionalising a process of consensus-building on drugs policy.

None of them imposes legal obligations on EU Member States, but the evaluation found that they have been successful in broadly directing collective action in the field of drugs, both within the EU and at international level, and promoting a shared model with a culture of defining priorities, objectives, actions and indicators for measuring performance.

The evaluation also found that the EU added value appears more pronounced in terms of demand reduction activities and emerging challenges. In international development cooperation Member States recognised the added value of collectively setting a common strategic framework for actions at the EU level.

The EU now has more of a ‘voice’ in international fora and international relations. This provides an important source of guidance for candidate countries, and a framework for bilateral cooperation with non-EU countries.

* 1. **Conclusion**

Overall, the evaluation confirmed that all stakeholders would broadly welcome a new Action Plan for 2017-2020. They considered it necessary to continue setting out precise priorities and actions relating to each objective, to assign responsibility and to formulate specific, measurable indicators. The comprehensive nature of the Strategy enables stakeholders to refine the focus of the priorities over its lifespan while maintaining a reasonable degree of coherence. In addition, stakeholders favoured updating the 2013-2016 Action Plan in response to new developments and emerging issues.

The evaluation found that some actions needed to be strengthened or added in order to keep up with developing issues and create more synergies with other EU policy areas such as the EU Health Strategy. It also points to the need for a greater level of focus on the use of new communication technologies in illicit drug production and trafficking and the role of internet in drug prevention. The evaluation shows that the omission of a discussion on recent trends in cannabis policy was noted by a wide range of stakeholders and represented one of the most frequent items raised when exploring whether there are any issues not covered by the Strategy.

The evaluation also indicates that there is room for improvement in implementation and access to risk and harm reduction measures across various Member States and that stakeholders from civil society expressed concerns about the extent and quality of these measures.

Finally, the evaluation found that a future Action Plan should continue to include actions to monitor NPS, to reduce demand for and supply of them, and to reduce harms associated with their use.

1. **The draft new Action Plan 2017-2020 - what is new and what has been updated?**

Building on the evaluation findings and recommendations, the Commission is proposing a draft EU Action Plan on Drugs 2017-2020, thus covering the remaining years of the existing EU Drugs Strategy, in force until 2020. Building on the results of the evaluation, the draft Action Plan maintains and strengthens existing actions to address challenges that continue to pose a threat to health and security. It also includes new actions to reflect developments since 2013 and address emerging challenges not covered previously. Some of the newly introduced actions, such as those addressing the use of new technologies for prevention or the comprehensive analysis of developments relating to cannabis policy models, are based on the evaluation’s findings. Others result from reflections emerging from sources such as the EU Drugs Market Report, policy developments at EU level notably in the context of the European Agenda on Security and contributions from the civil society. Such actions include:

* gathering evidence of potential connections between drug trafficking and
  + the financing of terrorist groups and activities;
  + migrant smuggling; and
  + trafficking in human beings
* the explicit inclusion of vulnerable groups in the drug demand actions

The new actions and updates as they relate to the five pillars of the Strategy are summarised below.

* 1. **Drug demand reduction**
* Stronger synergies will be created between the new Action Plan and the EU Health Strategy, particularly as regards the **use of information and communications technologies (ICT) for prevention purposes.** The use of ICT is key to raising awareness, especially among children and young people, of the risks and consequences of illicit drugs use.[[18]](#footnote-18)
* Account is taken of the recent work of the Horizontal Drugs Group (HDG) **on the misuse of prescribed opioids and other psychoactive medicines**[[19]](#footnote-19).
* In the light of population ageing in the EU there is a need to address the emerging challenge of **ageing drug users**, as also outlined in the EU Health Strategy[[20]](#footnote-20).
* **Drug use in vulnerable communities** will be addressed by refining the targeted measures in the Action Plan 2013-2016[[21]](#footnote-21).
* **Stronger focus on risk and harm reduction** measures, aimed at minimising the adverse health and social consequences of drug abuse, play a central role in effective drugs policy, including in prison settings[[22]](#footnote-22).
* Implementation and monitoring of the 2015 Council conclusions[[23]](#footnote-23) on **minimum quality standards in drug demand reduction** in the EU[[24]](#footnote-24).
  1. **Drug supply reduction**
* Stronger focus on judicial cooperation in drugs related cases at EU level is required. To get a fuller picture of the impact of supply reduction efforts, Europol, Eurojust and the EMCDDA should maintain their work to collect **indicators and complement data collection**, where possible,withqualitative and contextual information[[25]](#footnote-25).
* There should be a focus on the continued implementation of the key indicators adopted by the 2013 Council conclusions on improving the **monitoring of drug supply in the EU**[[26]](#footnote-26). Seven indicators have been developed along with a roadmap for their implementation. Full data collection for most of them is ongoing or will start in 2017[[27]](#footnote-27).
* The **New Psychoactive Substances** (**NPS)** legislative package should be rapidly adopted and swiftly implemented; monitoring the effects of the new legislative measures will also be required in the next years[[28]](#footnote-28).
* Implementation[[29]](#footnote-29) of the EU legislation on **drug precursors** which was strengthened in 2013 with the adoption of significant amendments to the two Regulations[[30]](#footnote-30).
* More attention should be given to **alternatives sanctions for drug-using offenders**. All Member States have at least one available and most have more than one[[31]](#footnote-31). The most commonly available sanctions are drug treatment and suspended sentences with a treatment option[[32]](#footnote-32).
* Greater focus on **the use of ICT in illicit drug production and trafficking[[33]](#footnote-33)**as established at the June 2016 expert meeting organised by the Commission [[34]](#footnote-34) in the context of the EU Internet Forum.
  1. **Coordination**
* **Greater coherence and coordination** with the other Council working groups would help the HDG fulfil its role of monitoring the implementation of the Strategy and ensure coherence between demand and supply reduction activities and detect relevant synergies[[35]](#footnote-35).
* More attention and time should be devoted to discussing the **implementation of the Action Plan** during HDG meetings[[36]](#footnote-36).
* As advocated by the EU in global fora, **further opportunities should be sought to increase civil society's participation** in the formulation, implementation, monitoring and evaluation of drugs policies at EU and national level[[37]](#footnote-37).
  1. **International cooperation**
* The evaluation found that there is scope for improving the **capacity of EU delegations** to engage in drugs issues and network with each other on regional basis.[[38]](#footnote-38)
* Greater focus should be placed on combating **illegal drug crop cultivation and** on enhancing **alternative development**[[39]](#footnote-39).
* In order to address adequately concerns as regards drug-related extrajudicial killings and the use of the death penalty, the EU should explore ways of **engaging with other countries whenever serious drug-related issues arise**[[40]](#footnote-40).
* Account is also taken of recent developments in the **Dublin Group[[41]](#footnote-41)**, which is looking at ways of modernising its working methods[[42]](#footnote-42).
* The relevant actors have not deemed it essential to holding an annual dialogue on EU and Member States' drug-related assistance to other countries so that action has been dropped from the draft Action Plan[[43]](#footnote-43).
* There is wide consensus that one key area in which the Strategy and Action Plan add value is enabling the EU to ‘**speak with one voice**’ in international fora, as demonstrated in the run-up to UNGASS 2016. Focus is needed now on the implementation of the UNGASS outcome and on the preparation of the 2019 review process of the 2009 Political Declaration and Action Plan on International Cooperation towards an integrated and balanced strategy to counter the world drug problem[[44]](#footnote-44)
  1. **Research, information, monitoring and evaluation**
* There should be clear **indicators to measure the impact** of EU funded projects[[45]](#footnote-45).
* Account is taken of work to **promote the scientific evaluation** of policies and interventions at national, EU and international level.[[46]](#footnote-46)
* To address a lack of solid evidence[[47]](#footnote-47), a new action[[48]](#footnote-48) focuses on documenting **potential connections between drug trafficking and:**
  + **the financing of terrorist groups and activities**, including any overlap between the established routes for drug production and trafficking areas and conflict zones and financing sources of terrorist cells in the EU;
  + **migrant smuggling,** creating synergies with the EU’s Action Plan to counter migrant smuggling[[49]](#footnote-49); **and**
  + **trafficking in human beings**, creating synergies with the 2012–2016 EU Strategy towards the Eradication of Trafficking in Human Beings**[[50]](#footnote-50)**.
* In the light of the current debate in some Member States and internationally, current **cannabis policy models** around the world and their impact will be analysed in more depth[[51]](#footnote-51).
* Account is taken of the work to improve the cooperation between the customs laboratories and the forensic laboratories networks, and between Commission services in the fight against **New Psychoactive Substances** (**NPS)[[52]](#footnote-52)**.

1. **Conclusions**

The mid-term assessment of the EU Drugs Strategy 2013-2020 and the final evaluation of the EU Action Plan on Drugs 2013-2016 have confirmed the continued relevance of the existing Strategy while also indicating a consensus among many stakeholders in favour of an updated Action Plan for the remaining years of the Strategy's duration.

Therefore, the Commission is proposing an Action Plan for 2017-2020 that maintains and strengthens existing actions to address challenges that continue to pose a threat to health and security. It also includes new actions to reflect developments since 2013 and addresses emerging challenges not covered previously.

The final evaluation of the Strategy and the 2017-2020 Action Plan, as required by the Strategy itself, will be presented in 2020. In 2019 an evaluation of the EMCDDA, including the Reitox system[[53]](#footnote-53), will also be carried out, as required by the EMCDDA founding Regulation[[54]](#footnote-54). As the above evaluations will provide valuable information on the implementation of the 2017-2020 EU Action Plan, a mid-term progress review will not be necessary.

The Commission will now enter into a dialogue on its proposed draft EU Action Plan on Drugs 2017-2020 with the European Parliament and the Council.

**ANNEX[[55]](#footnote-55)**

# Drug demand reduction

Contribute to a measurable reduction in the use of illicit drugs, in problem drug use, in drug dependence and in drug-related health and social harms as well as contributing to a delay in the onset of drug use

| **Objective** | **Action** | **Timetable** | **Responsible party** | **Indicator(s)** | **Data collection/ assessment mechanisms** |
| --- | --- | --- | --- | --- | --- |
| 1. Prevent drug use and, secondly, delay the onset of drug use | 1. Improve the availability and effectiveness of **evidence-based[[56]](#footnote-56)** prevention measures that take account of: 2. population risk factors such as age; gender; cultural and social factors; 3. situational risk factors such as homelessness; **migration and asylum seeking, d**rug use in nightlife and recreational settings; the workplace; and driving under the influence of drugs; and 4. individual risk factors such as mental health; problem behaviour and psychosocial development; and other factors known to affect individual vulnerability to drug use such as genetic influences and family circumstances | Ongoing | MS | * Overarching indicators 1, **11,** 12 * Level of provision at MS level of evidence-based universal and environmental prevention measures * Level of provision at MS level of **evidence-based** targeted prevention measures, including family and community based measures * Level of provision at MS level of **evidence-based** indicated prevention measures | EMCDDA Reporting  Reitox National Reports  MS reporting on results of measures |
| 1. In addition to the prevention of drug use, strengthen and better target prevention and diversionary measures to delay the age of first use of illicit drugs | Ongoing | MS | * Overarching indicators 1, 5, 12 * Level of provision at MS level of evidence based prevention and diversionary measures that target young people in family, community, and formal/non-formal education settings | EMCDDA Reporting  MS reporting on results ofmeasures |
| 1. **Exchange of best practices in targeting children and young people in prevention actions, including:** 2. **programmes and campaigns in formal and non/formal education settings;** 3. **online programmes and campaigns;** 4. **cooperation with internet companies for prevention purposes; and** 5. **ways of harnessing social media to better understand drug use and improve demand reduction responses** | **Ongoing** | **MS**  **Civil society**  **EMCDDA** | * **Type of exchanges of best practices between MS** * **Positive evaluations of behavioural outcomes of best practice interventions (where available)** | **EMCDDA best practices portal**  **MS reporting**  **Civil society reporting** |
| 1. Raise awareness of the risks and consequences associated with the use of illicit drugs and other psychoactive substances, **including by cooperating with internet companies and prevention experts to target children and young people better** | Ongoing | MS  COM  EMCDDA | * Overarching indicators 5, 12 * Level of awareness in general and youth populations of healthy lifestyles and of the risks and consequences of the use of illicit drugs and other psychoactive substances | EMCDDA Reporting  Eurobaro-meter surveys  ESPAD  HBSC |
|  | 1. Enable a more informed response to the challenge of the misuse of ~~prescribed and ‘over the counter’~~~~opioids~~ ~~and other~~ psychoactive medicines | 201**7*-***20**20** | MS  **Council WP** (HDG)  EMA  EMCDDA | * ~~Collation of data by MS on levels and patterns~~~~of prescribing of psychoactive medicines by end 2014~~ * Number of initiatives that focus on the promotion of appropriate use of ~~prescribed and ‘over the counter’~~~~opioids and other~~ psychoactive medicines * **Collation of evidence and international examples on how to reduce the risks of diversion and abuse of psychoactive medicines** * **Training of medical practitioners and other health professionals in the use of medication to control pain and treat suffering** | MS Reporting  **EMCDDA**  ~~Report of Alice RAP project~~ |
| 2. Enhance the effectiveness of drug treatment and rehabilitation, including services for people with co-morbidity, to reduce the use of illicit drugs; problem drug use; the incidence of drug dependency and drug-related health and social risks and harms and to support the recovery and social re/integration of problematic and dependent drug users **and of vulnerable communities, including by building synergies with the EU Solidarity Corps.** | 1. Develop and expand the diversity, availability, coverage and accessibility of **evidence-based** comprehensive and integrated treatment services. **Ensure that these services** address polydrug use (combined use of illicit and/or licit substances including alcohol **and tobacco) and the emerging needs of the ageing drug-using population and gender-specific issues. Develop early intervention/treatment and therapy programmes for child and adolescent drug users.** | Ongoing | MS | * Overarching indicators 1, 6, 11 * Extent of the diversity of **evidence-based** comprehensive and integrated treatment services at MS level including those which address polydrug use **and the needs of the ageing drug-using population** * MS data on treatment retention and outcomes | EMCDDA Reporting  Reitox  National Reports  EMCDDA Best Practice Portal  **EU Drugs Strategy and Action Plan final evaluation**  **MS reporting** |
| 1. Expand the provision of rehabilitation/recovery services with an emphasis on services that: 2. focus on providing a continuum of care through case management and interagency collaboration for individuals; 3. focus on supporting the social re/integration (including the employability **and housing**) of problem and dependent drug users **including prisoners** **and ageing drug users, where relevant;** 4. Strengthen the diagnostic process and the treatment of psychiatric and physical co- morbidity involving drug use**, for e.g. with rapid testing for hepatitis B and C and HIV as well as other sexually transmitted infections and tuberculosis, in line with the minimum quality standards on drug demand reduction adopted by the Council in 2015;** 5. **take account of gender-specific needs; and** 6. **reach out to vulnerable communities, including children and teenagers, ethnic minorities, migrants and asylum seekers, LGBTI, commercial sex workers and prisoners, people living with HIV/AIDS and the homeless.** | Ongoing | MS | * Overarching indicator 11   MS data on:   * Extent of increase in rehabilitation/recovery services adopting case management and inter-agency approaches * **Extent of increase in the number of gender specific rehabilitation/recovery programmes** * Extent of increase in the number of **comprehensive community care** programmes, specifically targeted at drug users with co-morbidity, involving partnerships between both mental health and drug rehabilitation/ recovery services **and prisons** * Level and duration of abstentions from consumption of illicit and/or licit drugs by people leaving drug treatment * Availability of treatment options to meet needs of people who experience relapses to drug use **and of ageing drug users** | EMCDDA Reporting  MS Reporting on  results ofservices |
| 1. **(a) Scale up access to harm reduction services e.g. needle and syringe exchange programmes, opioid substitution treatment, take-home naloxone programmes** ~~Ensure that treatment and outreach services incorporate greater access to risk and harm reduction options~~ to lessen the negative consequences of drug use and to substantially reduce the number of direct and indirect drug-related deaths and infectious blood borne diseasesassociated with drug use but not limited to HIV andviral hepatitis**,** as well as sexually transmittable diseases and tuberculosis   **(b) Identify and overcome barriers in access to treatment for hepatitis C among people who inject drugs, including prisoners and other vulnerable groups**  **(c) Exchange best practices on risk and harm reduction measures e.g. needle and syringe exchange programmes, opioid substitution treatment, drug consumption rooms, take-home naloxone programmes, peer based interventions, outreach treatment programmes, hepatitis C treatment, pill testing, self-testing for HIV/AIDS, etc.** | Ongoing | MS  **EMCDDA**  **COM**  **Civil Society Forum on Drugs**  **Civil Society Forum on HIV/AIDS, Viral Hepatitis and Tuberculosis** | * Overarching indicators 2, 3, 4, 11 * Extent of increased availabilityof and access to evidence basedrisk and harm reduction measures in MS * **Type of exchanges of best practices on risk and harm reduction measures** * **Number of MS reaching the WHO recommendation of a minimum threshold of 200 sterile needles and syringes distributed per injecting drug user per year** * **Coverage of opioid substitution treatment programmes among people with opioid dependence** * **Extent of increased availability of take home naloxone programmes and nightlife harm reduction programmes** * **Number of programmes facilitating the access of people who inject drugs into treatment for the hepatitis C virus (HCV) and people covered** * **Number of harm reduction programmes targeting vulnerable communities e.g. ethnic minorities, migrants and asylum seekers, LGBTI, commercial sex workers and prisoners** * **Degree of implementation of ECDC/EMCDDA guidance on prevention and control of infectious diseases among people injecting drugs** * **Degree of implementation of EU minimum quality standard in drug demand reduction III *(Treatment services provide voluntary testing for blood-borne infectious diseases, counselling against risky behaviours and assistance to manage illness)*** | EMCDDA Reporting  Reitox National Reports  MS Reporting ~~on services~~ |
| 1. Scale up the development, availability and coverage of health care measures for drug users inprisonand after release with the aim of achieving a quality of care equivalent to that provided in the community | Ongoing | MS | * Overarching indicator 10 * Availability of servicesfor drug usersin prisons **(including opioid substitution treatment and needle and syringe exchange programmes)** and the extent to which prison health care policies and practices incorporate care models comprising best practice**s** in needs assessment and continuity of care for prisoners during imprisonment * Extent of decrease in drug-related physical and mental health problems amongst prisoners * Extent to which prison based services and community based services provide continuity of care for prisoners upon releasewith particular emphasis on avoiding drug overdoses | EMCDDA Reporting  Reitox National Reports  MS Reporting on services |
| 3. Embed co-ordinated, best practice and quality approaches in drug demand reduction | 1. Implement **the** EU minimum quality standards **adopted by the Council in 2015[[57]](#footnote-57)** that help bridge the gap between science and practice, for: 2. environmental, universal, selective and indicated prevention measures; 3. early detection and intervention measures; 4. risk and harm reduction measures; and 5. treatment, rehabilitation, social integration and recovery measures   **and monitor their implementation.** | 201**7**-20**20** | Council  **Council WP** (HDG)  MS  COM  EMCDDA | * ~~Consensus achieved by MS~~~~on minimum quality standards building on previous EU preparatory studies~~ * **Evidence review of drug demand reduction programmes implemented in accordance with the standards;** * **Number of specialist training programmes available for practitioners in drug demand reduction and/or estimated number of practitioners reached by specialist training programmes;** * **Involvement of civil society in the implementation of the standards, including in planning and introduction** * **Number and impact of projects and programmes supported at EU level that promote the exchange of best practices in the implementation of these standards** * **Engagement in inter-ministerial cooperation to support implementation of these standards.** | EMCDDA Best Practice Portal  ~~COM Biennial Progress Report~~  **MS reporting**  **EU Drugs Strategy and Action Plan final evaluation** |

# Drug supply reduction

Contribute to a measurable reduction of the availability and supply of illicit drugs in the EU

| **Objective** | **Action** | **Timetable** | **Responsible party** | **Indicator(s)** | **Data collection/ assessment mechanisms** |
| --- | --- | --- | --- | --- | --- |
| 4. Enhance effective law enforcement co-ordination and co-operation within the EU to counter illicit drug activity, in coherence, as appropriate, with relevant actions determined through the EU policy cycle | 1. Utilise to best effect available intelligence and information sharing law enforcement instruments, channels and communication tools used to collate and analyse drug-related information | Ongoing | MS  Europol  Eurojust  **Council WP** (COSI) | * Overarching indicator 7 * Extent of high impact intelligence led and targeted activities, of joint operations, joint investigation teams and cross border cooperation initiatives focusing on criminal organisations engaged in illicit drug activity * Increased use of Europol’s drug-related information-sharing, analysis and expert systems * Results achieved from EMPACT projects and bilateral and multilateral initiatives * **Number of drug-related cases referred to Eurojust and Europol, including qualitative, contextual information about the cases** | ~~EMCDDA Reporting~~  ~~EU Agencies~~  **Europol** Reporting  **Eurojust Reporting**  EMPACT Driver Reports |
| 1. Identify and prioritise the most pressing threats associated with drug-related organised crime | **2017** | Council  **Council WP** (COSI)  Europol  MS  COM | * EU Policy Cycle and Crime priorities for 201**7**-20**21** in place | ~~Council Conclusions on EU Policy Cycle~~  EU SOCTA  **Multi-annual Strategic Plans (MASPs)**  ~~EMPACT Evaluation~~  **EMPACT Driver Reports**  **Europol Directors' Report** |
| 1. Strengthen CEPOL’s training for law enforcement officers in relation to illicit drug production, trafficking **and financial crime,** particularly training methods and techniques 2. to combat the use of new communication technologies in illicit drug production and trafficking; 3. to enhance asset confiscation; 4. to combat money laundering; 5. to detect and dismantle illicit clandestine laboratories and cannabis cultivation sites. | 201**7**-20**20** | MS  CEPOL  Europol  **Council WP** (COSI)  COM | * Training needs assessment carried out **regularly** * Availability and uptake of relevant training courses * Number of law enforcement officers trained and effectively deployed as a result | ~~COM Biennial Progress~~  ~~Report~~  CEPOL Annual Report  CEPOL Curricula  ~~EMPACT Evaluation~~  **EMPACT Driver Reports** |
|  | 1. Improve counter narcotic activities through strengthening and monitoring the effectiveness of regional information-sharing platforms and regional security-sharing platforms with the aim of disrupting and suppressing emerging threats from changing drug trafficking routes | Ongoing | COM  MS  Europol  **Council WP** (COSI)  Regional Information-  Sharing Platforms  Regional Security-Sharing Platforms | * Overarching indicator 7 * Number of intelligence led activities leading to the disruption and suppression of drug trafficking routes * Level of information sharing through effective activity of the liaison officer network | ~~EMCDDA Reporting~~  Security/ Information -sharing Platforms and Evaluation Reports  EU SOCTA  ~~EMPACT Evaluation~~  **EMPACT Driver Reports**  **Europol Directors' Report**  **MAOC(N)[[58]](#footnote-58)** |
| 1. Strengthen actions to prevent the diversion of drug precursors and pre-precursors for use in the illicit manufacture of drugs | Ongoing | MS  Europol  COM  **Council WP** (CUG  COSI) | * Number of cases and quantity of stopped or seized shipments of precursors intended for illicit use * Results achieved from EMPACT projects * Use of Pre-Export Notification (PEN) Online System and increased use of the Precursors Incident Communication System (PICS) * Number of joint follow up meetings and other activities linked to the prevention of the diversion of precursors and pre-precursors | Reports from EU and MS Law Enforcement Agencies  ~~EMPACT Evaluation~~  **EMPACT**  Driver Reports  **Europol Directors' Report** |
| 1. Counter cross-border drug trafficking, **including through container and parcel shipments,** and improve border security notably at EU seaports, airports and land border crossing points through intensified efforts, including information and intelligence sharing, by relevant law enforcement agencies | Ongoing | MS  Europol  **Council WG**  (CCWP  COSI) | * Increased number of multi-disciplinary/multi-agency joint operations and cross border cooperation initiatives * Number of effective Memoranda of Understanding (MOU) agreed between law enforcement agencies and relevant bodies such as airlines, air express couriers, shipping companies, harbour authorities and chemical companies * Results achieved from EMPACT projects * Improved intelligence and information sharing on cross-border drug trafficking utilising, *inter alia,* available border surveillance systems   airports and land border crossing points | ~~COM Biennial Progress~~  ~~Report~~  EMPACT ~~Evaluation~~ Driver Reports  **Europol Directors' Report**  **Europol reporting**  MS Reporting |
| 1. **Implement the key indicators on drug supply reduction adopted by the Council in 2013[[59]](#footnote-59)** | 201**7**-20**20** | COM  MS  Council  **Council WP** (HDG)  EMCDDA  Europol | * ~~Roadmap developed and agreed on the implementation of key drug supply indicators MS agreement reached on key drug supply indicators~~ * **number and quantity of drug seizures** * **purity and content of drugs** * **drug prices** * **drug production facilities dismantled** * **drug law offences** * **drug availability in population surveys** * **market size estimates** | Overview of existing supply data collection in MS  EMCDDA Reporting  **Europol reporting**  ~~COM Biennial Progress Report~~ |
| 5. Enhance effective judicial co-operation and legislation within the EU | 1. Strengthen EU judicial co-operation in targeting cross-border drug trafficking, money laundering, and in the confiscation of the proceeds of drug-related organised crime | 201**7**-20**20** | Council  COM  MS  Eurojust | * ~~Adoption and~~ **T**imely implementation of agreed EU measures and legislation on (a) confiscation and recovery of criminal assets**[[60]](#footnote-60);** (b) money laundering**[[61]](#footnote-61);** (c) approximation of drug trafficking offences and sanctions across the EU[[62]](#footnote-62) * Increased number of financial investigations and confiscations in relation to the proceeds of drug-related organised crime through EU judicial cooperation * Timely and effective responses to mutual assistance requests and European Arrest Warrants in relation to illicit drug trafficking | Eurojust Reporting  **MS reporting**  ~~COM Biennial Progress Report~~ |
| 1. Adopt **and implement** new EU legislative measures to address the emergence, use and rapid spread of new psychoactive substances | 201**7**-20**20** | COM  Council  **Council WP** (HDG)  MS  **EMCDDA**  **Europol** | * EU legislation in place * Implementation of EU legislation in MS * **Development of EU guidelines for the information exchange and risk assessment procedures** * **Monitor the effects of new legislative measures with a special focus on the replacement-effect in the illegal drug market** | ~~COM Biennial Progress Report~~  **MS reporting** |
| 1. **Implement effectively** EU legislation on drug precursors to prevent their diversion without disrupting lawful trade | Ongoing | Council  COM  MS | * Implementation of Regulations of the European Parliament and of the Council on drug precursors amending both Council Regulation (EC) No. 111/2005 and Regulation (EC) No. 273/2004 | ~~COM Biennial Progress Report~~  EU Annual Report on Drug Precursors |
| 1. Combat the use of certain pharmacologically active substances (as defined in EU Directive 2011/62) as cutting agents for illicit drugs | Ongoing | MS  COM  EMA  ~~EMCDDA~~  Europol | * Number of seizures of active substances usedas cutting agents for illicit drugs * Timely implementation of new EU legislative requirements aimed at securing the supply chain for active substances under Directive 2011/62/EU, the Falsified Medicines Directive | Reports from the CCWP and CUG  MS Reporting |
|  | 1. Members States to provide **and apply**, where appropriate and in accordance with their legal frameworks, alternatives to coercive sanctions ~~(such as education, treatment, rehabilitation, aftercare and social integration)~~ for drug using offenders, **including:** 2. Education 3. **(Suspension of sentence with)** treatment 4. **Suspension of investigation or prosecution** 5. Rehabilitation 6. Aftercare and social integration   **and develop the Fundamental rights dimension as a key factor to better balance repression and promote rehabilitation.** | 201**7-2020** | MS  **Council** (HDG) | * Increased availability and implementation of alternatives **to coercive sanctions** ~~prison~~ for drug-using offenders in the areas of education, treatment, rehabilitation, aftercare and social integration. * Increased monitoring, implementation and evaluation of alternatives to coercive sanctions * **Type and number of alternatives to coercive sanctions provided for and implemented by MS** * **Information on beneficiaries of alternative sentences who reoffend within five years** | Reitox National Reports  **MS** **reporting** |
| 6. Respond effectively to current and emerging trends in illicit drug activity | 1. **Identify strategic responses to address the role of new communication technologies and the hosting of associated websites, in the production, marketing, purchasing and distribution of illicit drugs, including controlled new psychoactive substances at national and EU level, including by:** 2. **Cooperation with industry** 3. **EU and national funding for relevant research and development of tools to support the work of law enforcement** 4. **Setting up of a glossary of terms** 5. **Setting up an inventory of existing monitoring tools for the web and darknet** 6. **Providing specialised training for law enforcement, customs and border guards, prosecutors and judges** 7. **Continuous and proactive monitoring of online marketplaces by law enforcement** 8. **Exchange of best practices with international partners** 9. **Streamlining of mutual legal assistance proceedings (and where applicable, mutual recognition), in line with the 09 June 2016 Council Conclusions on improving criminal justice in cyberspace[[63]](#footnote-63)** | **2017-2020** | Council  COM  **Council WP** (HDG, **COSI)**  MS  Europol  **CEPOL**  **EMCDDA** | * Results achieved from law enforcement   actions targeting drug-related crime via the internet   * Increased number of joint operations and   cross border cooperation initiatives   * **Number and impact of funded research projects and tools developed to support law enforcement** * **Number of agreements/discussions with relevant industry partners** * **Setting up of a glossary of terms** * **Setting up of an inventory of monitoring tools** * **Numbers of training sessions for relevant stakeholders** * **Number of meetings with international partners in which the action was discussed** | ~~Progress~~ **Interim** Review of **the** EU Policy Cycle ~~Priorities~~  EMPACT ~~Evaluation and~~  Driver Reports  **Europol Directors' Report**  **CEPOL Statistics/Annual Report**  MS Reporting  Reports from EU Agencies  **COM** |

**3.** Co-ordination

Member States and EU to effectively co-ordinate drugs policy

| **Objective** | **Action** | **Timetable** | **Responsible party** | **Indicator(s)** | **Data collection/ assessment mechanisms** |
| --- | --- | --- | --- | --- | --- |
| 7. Ensure effective EU co-ordination in the drugs field | 1. Enhance information sharing between the HDG and other relevant Council Working Groups **and in particular COSI to enhance coordination as regards the drug supply reduction pillar**   **Enhance information sharing between the HDG and other relevant geographical and thematic Council Working Groups including: COAFR, COASI, COEST, COLAT, COWEB, CONUN and COHOM** | Ongoing | PRES  Council  EEAS  **Council WP** (HDG) | * Extent to which the EU Drugs Strategy/and Action Plan are taken into account in the Programmes of other Council Working Groups including **COSI,** COAFR, COASI, COEST, COLAT, COWEB, **CONUN and COHOM.** * **Regular information point on the HDG agenda (once per Presidency) on activities linked to drug-related priorities of the EU Policy Cycle (based on EMPACT reporting) in the presence of the COSI Support Group chair, if relevant** | Council Working Group (HDG) reporting  **Presidency reporting** |
| 1. Each Presidency may convene meetings of the National Drugs Co-ordinators, and of other groupings as appropriate, to consider emerging trends, effective interventions and other policy developments of added value to the EU Drugs Strategy and to MS | Biannually | PRES  MS | * Extent to which National Drug Co-ordinators’ meeting agenda reflects developments, trends and new insights in policy responses and provides for improved communication and information exchange | Presidency Reporting |
| 1. The HDG will facilitate (a) monitoring of the implementation of the Action Plan through thematic debates; and (b) an annual dialogue on the state of the drugs phenomenon in Europe | (a) ~~Biannually~~**Ongoing**  (b) Annually | PRES  **Council WP** (HDG) MS  COM  EMCDDA  Europol | * Extent of implementation of the Action Plan * **Number of actions from the Action Plan addressed in thematic debates in the HDG** * Timeliness of dialogue atthe HDG on latest drug-related trends and data | Presidency Reporting |
| 1. Ensure consistency and continuity of MS and EU actions across Presidencies to strengthen the integrated, balanced and evidence-based approach to drugs in the EU | ~~Biannually~~**Ongoing** | PRES  PRES Trio  MS  COM  **Council WP** (HDG)  EMCDDA  Europol | * Extent of consistency and continuity of actions across Presidencies * Advancement in implementation of EU Drugs Strategy priorities across Presidencies | Presidency Reporting |
| 1. Ensure co-ordination of EU drugs policies and responses, to support international co-operation between the EU, third countries and international organisations | Ongoing | EEAS  COM  **Council WP** (HDG)  MS | * Level of consistency and coherencein the objectives, expected results and measures foreseen in EU actions on drugs * Inclusion of drug-related priorities in strategies of relevant EU bodies * Intensified co-operation between the HDG and the geographical/regional **and thematic** working groups, including COAFR, COASI, COEST, COLAT, COWEB, **CONUN and COHOM** | Annual EEAS Report to the HDG  ~~COM Biennial Progress Report~~ |
|  | 1. Achieve a co-ordinated and appropriate level of resources at EU level and Member State level to fulfil the priorities of the EU Drugs Strategy | Annually | MS  COM  EEAS  Council  **Council WP** (HDG) | * Overarching indicator 14 * Amount of funding at EU level, and where appropriate, MS level * Extent of co-ordination on drugs-related financial programmes across Council Working Groups **and COM** | EMCDDA Reporting  **COM reporting**  ~~COM Biennial Progress Report~~ |
| 8. Ensure effective co-ordination of drug-related policy at national level | 1. Co-ordinate actions on drugs policy between Government Departments/Ministries and relevant agencies at MS level and ensure appropriate multi-disciplinary representation on, or input to, HDG delegations | Ongoing | MS | * Overarching indicator 14 * Effectiveness of a horizontal drug policy co-ordination mechanism at MS level * Number of cross-cutting actions in drug demand and supply reduction at Member State level | EMCDDA Reporting  Reitox National Reporting  ~~COM Biennial Progress Report~~  MS Reporting |
| 9. Ensure the participation of civil society in drugs policy | 1. Promote and ~~support~~ **strengthen** dialogue with, and involvement of, civil society and the scientific community in the **formulation, implementation, monitoring and evaluation** ~~development,~~ of drugs policies at MS and EU levels | Ongoing | MS  COM  **Council WP** (HDG)  PRES  **Civil Society Forum on Drugs** | * Timely dialogues between EU Civil Society Forum on Drugs and the HDG during each Presidency period * Engagement of EU Civil Society Forum in reviewing implementation of the EU Drugs Action Plan * Level of involvement of civil society in MS and EU drugs policy **formulation,** ~~development and~~ implementation, **monitoring and evaluation** ~~with particular regard to the involvement of drug users, clients of drug-related services and young people~~ * Timely dialogue between the scientific community (natural and social sciences, including neuroscience and behavioural research) and the HDG * **Development of a database to facilitate communication within EU civil society on matters relating to EU and MS drugs policies** | ~~COM~~  ~~Biennial Progress~~  ~~Report~~  Feedback from EU Civil Society Forum on Drugs and from Civil Society Representatives at MS **and EU** level  MS Reporting  Feedback from Scientific Community through the EMCDDAScientific Committee |

**4.** International Co-operation

Strengthen dialogue and cooperation between the EU and third countries and international organisations on drugs issues in a comprehensive and balanced manner

| **Objective** | **Action** | **Timetable** | **Responsible party** | **Indicator(s)** | **Data collection/ assessment** **mechanisms** |
| --- | --- | --- | --- | --- | --- |
| 10. Integrate the EU Drugs Strategy within the EU's overall foreign policy framework as part of a comprehensive approach that makes full use of the variety of policies and diplomatic, political and financial instruments at the EU's disposal in a coherent and co-ordinated manner | 1. Ensure policy coherence between the internal and external aspects of the EU drugs policies and fully integrate drugs issues within the political dialogues and framework agreements between the EU and its partners and in the EU advocacy on global issues or challenges | Ongoing | COM  EEAS  PRES  **Council WP** (HDG)  MS | * Overarching indicator 13 * Drug policy priorities increasingly reflected in EU’s external policies and actions * Inclusion of drug-related priorities in EU strategies with third countries and regions * Number of agreements, strategy papers, action plans in place | EEAS Reporting  ~~Mid-Term Review of EU Drugs Strategy~~  ~~COM Biennial Progress Report~~ |
| 1. Ensure that the policy priorities and the balance between demand and supply reduction are well reflected in policy options and in the programming, implementation **and monitoring** of external assistance, particularly in source and transit countries, through projects involving: 2. development of integrated, balanced and evidence-based drug policies; 3. supply reduction; 4. the prevention of the diversion of drug precursors and pre-precursors; 5. drug demand reduction; and 6. alternative development measures | Ongoing | COM  MS  EEAS | * Extent to which EU’s Drug policy priorities, especially the balance between demand and supply reduction, are reflected in funded priorities and projects * Level of implementation of co-ordinated actions in action plans between the EU and third countries and regions * Number of third country national strategies and action plans that incorporate integrated drug policies | ~~COM Biennial Progress Report~~  EEAS Reporting on Programming  **COM and MS Programme Monitoring and Evaluation Reports** |
| 1. Improve capacity and strengthen the role of EU Delegations to enable them to proactively engage on drugs policy issues **and effectively report back on the local situation on drugs** | 201**7**-20**20** | EEAS  COM  MS | * Relevant expertise, training and policy guidance provided to EU Delegations * Regional networking among EU Delegations on drug issues enhanced * Co-ordination with MS enhanced | EEAS  **COM** Reporting  EU Delegations |
| ~~Ensure an appropriate level of EU and MS funding and expertise to further strengthen and support third countries' efforts in addressing and preventing illicit drug crop cultivation, through rural development measures, in order to deal with the challenges to public health, safety and security~~ | ~~Ongoing~~ | ~~MS~~  ~~EEAS~~  ~~COM~~ | * ~~Number of third country national policies, strategies and action plans that incorporate integrated approaches to the problem of illicit drug crop cultivation~~ * ~~Improvements in human development indicators in drug-cultivating areas~~ * ~~Number of rural development projects and programmes, funded by the EU and MS in regions where illicit crop cultivation is taking place, or in regions at risk of illicit crop cultivation~~ * ~~Reported local decrease in illicit drug crop cultivation in the long-term~~ | ~~EU and MS Project and Programme Monitoring and Evaluation Systems and Reports~~  ~~UNDP Human Development Reports~~  ~~Third country reports~~ |
| 1. Promote and implement the EU approach to alternative development (consistent with the EU Drugs Strategy 2013-2020; the EU Approach to Alternative Development and the United Nations Guiding Principles on Alternative Development 2013) in co-operation with third countries, taking into account human rights, human security and specific framework conditions, including: 2. incorporating alternative development into the broader agenda of Member States, encouraging third countries that wish to do so to integrate alternative development into their national strategies; 3. contributing to initiatives that aim to reduce poverty, conflict and vulnerability by supporting sustainable, legal and gender sensitive livelihoods for people who were previously, or are currently, involved in illicit drug production 4. **providing an appropriate level of EU and MS funding and expertise to further strengthen and support non-EU countries' efforts in addressing and preventing illicit drug crop cultivation, through rural development measures and illicit drug production through law enforcement and judicial cooperation** | Ongoing | MS  COM  EEAS | * Number of third country national policies, strategies and action plans that incorporate**:**    + integrated approaches to the problem of illicit drug cultivation and   + effectively organised alternative development initiatives * Number of evaluated projects that demonstrate positive outcomes relating to sustainable, legal and gender sensitive livelihoods * Improvements in human development indicators * **Number of rural development projects and programmes, funded by the EU and MS in regions where illicit crop cultivation is taking place, or in regions at risk of illicit crop cultivation** * **Reported local decrease in illicit drug crop cultivation in the long-term** | Third countries’ implementation reports of National Drugs Strategies  EU and MS Project and Programme Monitoring and Evaluation Reports  UNDP Human Development Reports  **Non-EU country reports** |
| 1. Support third countries, including civil society in those countries, to develop and implement risk and harm reduction initiatives particularly where there is a growing threat of transmission of drug-related blood borne viruses associated with drug use including but not limited to HIV and viral hepatitis, as well as sexually transmittable diseases and tuberculosis | Ongoing | MS  COM  EEAS | * Number and quality of risk and harm reduction initiatives developed * Prevalence of drug-related deaths in third countries and drug-related blood borneviruses including but not limited to HIV and viral hepatitis, as well as sexually transmittablediseases and tuberculosis | Third country Reports  ~~COM Biennial Progress Report~~  WHO Reports |
| 1. Support third countries to tackle drug-related organised crime, including drug trafficking, by: 2. intelligence-sharing and the exchange of best practices; 3. strengthening counter-narcotics capacity and developing expertise of source and transit countries; 4. working with international partners to tackle the enablers of drug trafficking such as corruption, weak institutions, poor governance and lack of financial regulatory controls; 5. strengthening co-operation in the field of asset identification and recovery, in particular through the creation of dedicated national platforms; and 6. intensifying regional and intra-regional co- operation 7. **incorporating rule-of-law and international human rights standards and principles in drug-related law enforcement measures** | Ongoing | MS  EEAS  COM  Europol  S | * Number and effectiveness of projects and programmes * Sustained reduction in drug trafficking | ~~COM~~  ~~Biennial Progress~~~~Report~~  **COM and** MS Reporting  Europol Reporting  EEAS Reporting  UNODC Annual World Drug Report |
|  | 1. (a) Reinforce co-operation and **conduct** ~~update and implement~~ dialogues, ~~Declarations and EU Drugs Action Plans~~ with partners, including:  * Acceding countries, candidate countries and potential candidates * European Neighbourhood Policy countries * United States of America, the * Russian Federation * Other countries or regions of priority notably: * Afghanistan and Pakistan * Central Asian Republics * China * Latin American and the Caribbean (CELAC) * Africa, in particular West Africa * **Iran**   **(b) Explore possibilities for engagement (such as bilateral dialogues, joint projects) with other non-EU countries on serious drug-related issues** | Ongoing | PRES Trio  COM  EEAS  MS | * Overarching indicator 13 * Strengthened co-operation in the field of drugs with relevant partners * Dialogues organised * Declarations agreed * Programmes and Action Plans implemented | EEAS Reporting  ~~Mid-Term Review of EU Drugs Strategy~~  ~~COM Biennial~~~~Progress Report~~  ~~EU Reporting Matrices~~  Implementation Reports of the relevant action plans |
| 1. Improve the Dublin Group consultative mechanism through intensified EU coordination and participation, better **formulation,** implementation and dissemination of its recommendations ~~of the Mini Dublin Group reports~~ | Ongoing | Dublin Group  COM  EEAS  MS | * Level of activity across Dublin Group structures including number of Dublin Group recommendations effectively implemented * **Achieved modernisation of the Dublin Group’s working methods** | Dublin Group Reports |
| ~~Hold an annual dialogue on EU and MS drugs-related assistance to third countries accompanied by a written update~~ | ~~From~~  ~~2014~~ | ~~COM~~  ~~EEAS~~  ~~MS~~ | * ~~Annual dialogue on funding held~~ | ~~COM~~  ~~Biennial Progress Report~~  ~~MS Reporting~~  ~~EEAS Reporting~~  ~~Project and Programme Monitoring and Evaluation System and Reports~~ |
| 1. Ensure that the promotion and protection of human rights are fully integrated in political dialogues and in the planning and implementation of relevant drugs-related programmes and projects including through the **implementation of the rights-based approach (RBA)** **and of tailored**  human rights guidance and impact assessment tool | Ongoing | COM  EEAS  MS | * Human rights effectively mainstreamed into EU external drugs action * Human rights guidance and assessment tool ~~developed and~~ implemented | ~~COM Biennial Progress Report~~  COHOM Annual Human Rights Report  MS Reporting |
| 12. Improve cohesiveness of EU approach and EU visibility in the United Nations (UN) and strengthen EU co-ordination with international bodies related to the drugs field | 1. Contribute to shaping the agenda on international drugs policy, including through: 2. action by EU and MS Delegations at the UN General Assembly and the Commission on Narcotic Drugs (CND); 3. **action by EU and MS delegations in all UN fora addressing drug-related matters (e.g. the UN General Assembly, World Health Assembly, Human Rights Council, High Level Political Forum on Sustainable Development)** 4. preparation, co-ordination and adoption of EU common positions and joint resolutions in the UN General Assembly and the CND**, including, ahead of the CND, on scheduling of substances,** and ensuring that the EU speaks with one strong voice in these and other international fora; 5. **the implementation of the recommendations of the 2016 UNGASS Outcome Document** 6. the **2019** review process of the 2009 UN Political Declaration and Action Plan on International Cooperation towards an Integrated and Balanced Strategy to Counter the World Drug Problem; and 7. **ensure the meaningful involvement of civil society in the review process** | Ongoing | EEAS  PRES  MS  COM  Council  **Council WP** (HDG) | * Overarching indicator 13 * Number of EU statements delivered at CND and UN fora * Number of EU common positions supported by other regions and international bodies * **Number of EU common positions concerning CND decisions on scheduling of substances** * **Outcome of the CND decisions on scheduling of substances** * Frequency with which EU speaks with a single effective voice in international fora and in dialogues with third countries * Level of successful adoption of EU resolutions at UN including at the CND * Effective promotion of EU policies in the UN, including at the CND * **Adoption of an EU Common Position Paper for the 2019 review process; EU contribution to the definition by the CND on the modalities for the 2019 process** * Outcome of the 2019 **review of the** UN Political Declaration and Action Plan on International Co-operation towards an Integrated and Balanced Strategy to Counter the World Drug Problem | EEAS Reporting  Mid-Term Review of the EU Drugs Strategy  COM Biennial Progress Report  Convergence Indicator  Mid-term Review  ~~UNGASS~~  **2019 review**Outcome |
| 1. Strengthen partnerships with the UNODC, WHO, UNAIDS and other relevant UN agencies, international and regional bodies and organisations and initiatives (such as the Council of Europe and the Paris Pact Initiative) | Ongoing | Council  EEAS  COM  PRES  **Council WP** (HDG)  **EMCDDA** | * Overarching indicators 13, **15** * Number ofinformation exchangesandactivities between the EU andrelevant international and regional bodies and organisations and initiatives * Effectiveness of partnerships with relevant bodies | EEAS Reporting  ~~Mid Term Review of the EU Drugs Strategy~~  ~~COM Biennial Progress Report~~ |
| 13. Support the process for acceding countries, candidate countries, and potential candidates to adaptto and alignwith the EU *acquis* in the drugs field, through targeted assistance and monitoring | 1. Provide targeted technical assistance, and other assistance and support as necessary, to acceding countries, candidate countries, and potential candidates to facilitate their adaptation to and alignment with the EU acquis in the drugs field | Ongoing | COM  MS  EMCDDA  Europol  Eurojust  FRONTEX  EEAS | * **Overarching indicator 15** * Increased compliance by countries with EU *acquis* * Number and quality of completed projects * National Drugs Strategies andnational drugs co-ordinating structures established | COM Biennial Progress Report  Acceding countries, candidate countries and potential candidates reports |

# Information, research, monitoring and evaluation

Contribute to a better understanding of all aspects of the drugs phenomenon and of the impact of measures in order to provide sound and comprehensive evidence for policies and actions

| **Objective** | **Action** | **Timetable** | **Responsible party** | **Indicator(s)** | **Data collection/ assessment mechanisms** |
| --- | --- | --- | --- | --- | --- |
| 14. Ensure adequate investment in research, data collection, monitoring, evaluation and information exchange on all aspects of the drug phenomenon | 1. Promote appropriate financing of EU-level drug-related multi-disciplinary research and studies including through EU related financial programmes (2014-2020) | 201**7**-20**20** | MS  COM  ~~EMCDDA~~ | * Amount and type of EU funding provided across the different programme and projects | COM  **reporting**  **at annual research dialogue** ~~Biennial Progress Report~~ |
|  | 1. Ensure that EU-supported projects: 2. take account of the priorities of the EU Drugs Strategy and Action Plan on Drugs; 3. take account of gaps in policy formulation; 4. deliver clear added value and ensure coherence and synergy; and 5. avoid duplication with research under other programmes and bodies 6. take account of the importance of behavioural research and neuroscience[[64]](#footnote-64) 7. **include clear indicators for measuring their impact** | 201**7**-20**20** | COM  EMCDDA | * The inclusion of the priorities of the EU Strategy and Action Plan on Drugs in the funding and assessment criteria of EU-funded drugs related research * Number, impact, complementarity and value of EU-funded drugs related research grants and contracts awarded * Number of EU-funded drugs related articles and research reports published in peer-reviewed journals with high impact factors * Annual debate at the HDG on drug- related research projects funded by the EU **including EMCDDA Scientific Committee recommendations on research priorities** | ~~COM Biennial Progress Report~~  Research project reports  EMCDDA Scientific Committee recommendations on research priorities  Science Citation Index and similar bibliometric tools  Strategic research agenda **developed by ERANID** |
|  | 1. Promote ~~scientific~~ **evidence-based** evaluations of policies and interventions at national, EU and international level | 2017-2020 | COM  MS EMCDDA | * Overarching indicator 14 * Regular progress review to the Council and European Parliament on Strategy and Action Plan implementation * **Number of countries following a structured approach, as outlined in the guide to commissioning and managing evaluations produced by the EMCDDA** * ~~External mid-term assessment of the Strategy/Action Plan completed – 2016~~ * ~~European guidelines for the evaluation of national drug strategies and action plans published~~ * Delivery of dedicated studies into the effectiveness and impacts of EU and international drug policies * ~~Completed evaluation of the implementation of the 2003 Council Recommendation on the prevention and reduction of health-related harm associated with drug dependence~~ | EMCDDA Reporting  ~~COM~~~~Biennial~~~~Progress Report~~  ~~Mid-term Assessment Report of EU Drugs Strategy~~  **EMCDDA Reporting**  ~~EMCDDA Scientific Committee Reporting~~  ~~Reports of Alice RAP and LINKSCH and ERA-net~~  Reitox National Reports |
|  | 1. **Gather evidence of potential connections between drugs trafficking and:** 2. **financing of terrorist groups and activities, including any overlap between the established routes for drug production and trafficking areas and conflict zones; and financing sources of terrorist cells in the EU from illicit activities, including drug trafficking;** 3. **migrant smuggling building synergies with the EU Action Plan against migrant smuggling (2015-2020) that foresees research and risk analysis between smuggling and other crimes such as drugs trafficking and including:**  * **A focus on vulnerable migrants and their potential exploitation for drugs trafficking purposes and/or as end users of drugs, in particular minors and women.** * **Exploration of any overlap between drugs trafficking and migrant smuggling criminal rings, modi operandi and routes.**  1. **trafficking in human beings building synergies with the EU legal and policy framework addressing trafficking in human beings including the EU Strategy towards the Eradication of Trafficking in Human Beings 2012–2016** | **2017-2020** | **MS**  **Commission**  **EU ATC**  **EMCDDA**  **Europol**  **Frontex**  **FRA**  **EIGE** | * **Number of projects funded at EU and national level** | **MS reporting**  **COM reporting**  **EU agencies reporting (EMCDDA Europol**  **FRONTEX and FRA in the framework of their regular reporting activities**  **EIGE in the framework of their regular reporting activities** |
| 15. Maintain networking and co-operation and develop capacity within and across the EU’s knowledge infrastructure for information, research, monitoring and evaluation of drugs, particularly illicit drugs | 1. In collaboration with relevant parties as appropriate, continue to provide comprehensive analyses of: 2. the EU drugs situation; 3. the dynamics of drug use within general populations and target groups **including ethnic minorities, migrants and asylum seekers, LGBTI, commercial sex workers and prisoners;** and 4. responses to drug use 5. **EU and international developments relating to cannabis policy models and their impacts** | Ongoing | EMCDDA  Europol  MS  **Civil Society Forum on Drugs**  **COM** | * Overarching indicators 1-15 * Current deficits in the knowledge base established and an EU level framework developed to maximise analyses from current data holdings * Number of overviews and topic analyses on the drug situation | EMCDDA Reporting  MS Reporting  **Civil Society Forum on Drugs**  **COM** |
| 1. Enhance training for those involved in responding to the drugs phenomenon | 201**7**-20**20** | MS  EMCDDA  CEPOL | * Number of initiatives at MS and EU level to train professionals in aspects of drug demand reduction and drug supply reduction * Number of initiatives at MS and EU level implemented to train professionals related to data collection and reporting of drug demand reduction and drug supply reduction | MS Reporting  ~~EMCDDA Training Report~~  CEPOL Annual Report  Reitox Annual Reports |
| 1. Enhance data collection, research, analysis and reporting on: 2. drug demand reduction; 3. drug supply reduction; 4. emerging trends, such as polydrug use and misuse of ~~prescribed controlled~~ **psychoactive** medicines, that pose risks to health and safety; 5. blood borne viruses associated with drug use including but not limited to HIV and viral hepatitis, as well as sexually transmittable diseases and tuberculosis; 6. psychiatric and physical co-morbidity; 7. drug problems among prisoners and the availability and coverage of drug demand reduction interventions and services in prison settings; and 8. other ~~drug-related consequences~~ **problems and consequences related both to licit and illicit substances** 9. **compliance of drugs policies with international human rights standards and principles** | Ongoing | MS  COM  EMCDDA  Europol  ECDC  EMA | * Increased availability and implementation of evidence-based and scientifically sound indicators on drug supply reduction and drug demand reduction * At MS level, extent of new research initiated on emerging trends such as polydrug use and the misuse of prescribed controlled medicines; blood borne diseases associated with drug use including but not limited to HIV and viral hepatitis, as well as sexually transmittable diseases and tuberculosis; psychiatric and physical co-morbidity; and other drug-related consequences * EU-wide study carried out on drug-related community intimidation and its impact on individuals, families and communities most affected and effective responses to it * Adoption of evidence-based and scientifically sound indicators on drug problems among prisoners | EMCDDA Reporting  MS Reporting  Harmonised data reports from EU bodies including EMCDDA  EU SOCTA |
| 1. Improve the capacity to detect, assess and respond effectively to the emergence and use of new psychoactive substances and monitor the extent to which such new substances impact on the number and profile of users | Ongoing | COM  MS  EMCDDA  Europol | * Overarching indicator 6 * Extent of new epidemiological, pharmacological and toxicological research initiated on new psychoactive substances and supported by MS and EU Research programmes * Extent of information, best practice and intelligence exchange * Extent of sharing by toxicology laboratories and by Research Institutes of toxicological and health data analyses on new psychoactive substances | EMCDDA Reporting  EMCDDA-Europol Implementation Report  Reports by laboratories and research institutes  Reitox National Reports |
| 1. Strengthen efforts to share forensic science data, including **support on the identification of new psychoactive substances,** laboratory reference standards on new psychoactive substances, **and the development of a common methodology for the identification of new substances** by enhancing co-operation **with the Commission's Joint Research Centre, and** through existing networks, such as the Drugs Working Group of the European Network of Forensic Science Institutes in the framework of the JHA Council Conclusions on the Vision for European Forensic Science 2020 **and the Customs Laboratories European Network** | 201**7-2020** | COM  MS  EMCDDA | * Overarching indicator 15 * Extent of sharing of forensic science data on new psychoactive substances, **supporting the identification of new psychoactive substances** * Ease of access to laboratory reference standards by forensic science laboratories**, customs laboratories** and institutes * **Progress on development of a common methodology for the identification of new psychoactive substances** | EMCDDA/ Europol Reporting  **COM reporting**  ~~COM Biennial Progress Report~~ |
|  | 1. Improve the ability to identify, assess and respond at MS and EU levels to (a) behavioural changes in drug consumption and (b) to **drug-related** epidemic outbreaks | Ongoing | MS  EMCDDA  ECDC  EMA | * Number and effectiveness of new drug-related public health initiatives developed and implemented * Number and effectiveness of existing initiatives that are adjusted to take account of drug consumption or epidemic outbreaks * Number and impact of early warning reports, risk assessment and alerts | Reitox National Reports  Early Warning System reports  EMCDDA Reporting |
| 16. Enhance dissemination of monitoring, research and evaluation results at EU and national level | 1. Member States continue to support EU monitoring and information exchange efforts, including co-operation with, and adequate support for, Reitox National Focal Points | Ongoing | MS  EMCDDA  **COM** | * Open-access outputs from EU funded studies disseminated * Extent to which Reitox National Focal Points funding and other resources match requirements * Number and effectiveness of Reitox National Focal Points dissemination initiatives | Web Dissemination including OpenAire, Cordis  EMCDDA website  Reitox National reports |

# Annex 1 - 15 Over-arching Indicators for the EU Action Plan on Drugs 2017-2020[[65]](#footnote-65)

1. Percentage of population who use drugs currently (within last month), used drugs recently (within last year), and who have ever used (lifetime use) by drug and age group (EMCDDA General Population Survey)
2. Estimated trends in the prevalence of problem and injecting drug use (EMCDDA Problem Drug Use)
3. Trends in druginduced deaths and mortality amongst drug users (according to national definitions)(EMCDDA Drug-related Deaths)
4. Prevalence and incidence, among injecting drug users, of infectious diseases attributable to drug use, including HIV and viral Hepatitis, sexually transmittable diseases and tuberculosis (EMCDDA Drug-related Infectious Diseases)
5. Trends in the age of first use of illicit drugs (European School Survey Project on Alcohol and Drugs (ESPAD), Health Behaviour in School-aged Children (HBSC) and General Population Drug Use Survey **(**EMCDDA Key Epidemiological Indicator)
6. Trends in numbers of people entering drug treatment (EMCDDA Treatment Demand) and the estimated total number of people in drug treatment (EMCDDA Treatment Demand and Health and Social Responses)
7. Trends in number of and quantities of seized illicit drugs (EMCDDA Drug Seizures: cannabis incl. herbal cannabis, heroin, cocaine, crack cocaine, amphetamine, methamphetamine, ecstasy, LSD and other substances)
8. Trends in retail price and purity of illicit drugs (EMCDDA Price and Purity: cannabis incl. herbal cannabis, heroin, cocaine, crack cocaine, amphetamine, methamphetamine, ecstasy, LSD, other substances and composition of drug tablets)
9. Trends in the number of initial reports of drug law offences, by drug and type of offence (supply vs use/possession)(EMCDDA Drug Offences)
10. Prevalence of drug use amongst prisoners (EMCDDA Drug Use in Prisons)
11. Assessment of availability, coverage and quality of services and interventions in the areas of prevention, harm reduction, social integration and treatment. (EMCDDA Health and Social Responses)
12. Evidence based interventions on prevention, treatment, social integration and recovery and their expected impact on drug use prevalence and problem drug use (EMCDDA Best Practice Portal)
13. Strong dialogue and co-operation, in the drugs related field, with other regions, third countries, international organisations and other parties (External Mid-Term Evaluation of Strategy/Action Plan; EEAS reporting)
14. Developments in national drug strategies, evaluations, legislation, co-ordination mechanisms and public expenditure estimates in EU Member States (EMCDDA)

15. Early Warning System on new psychoactive substances (EMCDDA/Europol) **and Risk Assessment on new psychoactive substances (EMCDDA)**

# Annex 2 - Glossary of Acronyms

|  |  |
| --- | --- |
| ~~Alice RAP~~ | ~~Addiction and Lifestyles in Contemporary Europe Reframing Addictions Project~~ |
| ~~ASEAN~~ | ~~Association of Southeast Asian Nations~~ |
| CCWP | Council of the EU - Customs Cooperation Working Party |
| CELAC | Comunidad de Estados Latinoamericanos y Caribeños (Community of Latin American and Caribbean States) |
| CEPOL | European Police College |
| ~~CICAD~~ | ~~La Comisión Interamericana para el Control del Abuso de Drogas (The Inter-American Drug Abuse Control Commission~~ |
| CND | Commission on Narcotic Drugs (UN) |
| COAFR | Council of the EU - Africa Working Party |
| COASI | Council of the EU - Asia-Oceania Working Party |
| COEST | Council of the EU - Working Party on Eastern Europe and Central Asia |
| COHOM | Council of the EU - Working Party on Human Rights |
| COLAT | Council of the EU - Working Party on Latin America |
| COM | European Commission |
| **CONUN** | **Council of the EU – United Nations Working Party** |
| COSI | Council of the EU - Standing Committee on Operational Cooperation on Internal Security |
| **Council WP** | **Council Working Party** |
| COWEB | Council of the EU - Working Party on the Western Balkans Region |
| CUG | Council of the EU - Customs Union Group |
| ECDC | European Centre for Disease Control |
| ~~ECOWAS~~ | ~~Economic Community of West African States~~ |
| EEAS | European Union External Action Service |
| EMA | European Medicines Agency |
| EMCDDA | European Monitoring Centre for Drugs and Drug Addiction |
| EMPACT | European Multidisciplinary Platform against Criminal Threats |
| ENFSI | European Network of Forensic Science Institutes |
| ERA-net | European Research Area – Network |
| **ERANID** | **European Research Area Network on Illicit Drugs** |
| ESPAD | European School Survey Project on Alcohol and Drugs |
| **EU** | **European Union** |
| **EUROJUST** | **European Judicial Cooperation Unit** |
| **EUROPOL** | **European Union Agency for Law Enforcement Cooperation** |
| EU SOCTA | EU Serious and Organised Crime Threat Assessment |
| FRONTEX | European Agency for the Management of Operational Cooperation at the External Borders of the Member States of the European Union |
| HBSC | Health Behaviour in School Aged Children survey |
| **HCV** | **Hepatitis C virus** |
| HDG | Council of the EU - Horizontal Working Group on Drugs |
| **HIV** | **Human immunodeficiency virus** |
| INCB | International Narcotics Control Board (UN) |
| JHA | Justice and Home Affairs |
| **LGBTI** | **Lesbian, Gay, Bisexual, Transgender/Transsexual and Intersexed** |
| **LSD** | **Lysergic acid diethylamide** |
| **MASPs** | **Multi-annual Strategic Plans (Europol)** |
| **MOU** | **Memorandum of Understanding** |
| ~~LINKSCH~~ | ~~The LINKSCH project is a comparative study of two major drug markets, cannabis and heroin, through the prism of the transit chains operating between Central Asia and the EU and those between North Africa and the EU~~ |
| MS | Member State |
| NPS  PEN | New psychoactive substances  UNODC/INCB developed Pre-Export Notification Online System |
| PICS | Precursors Incident Communication System |
| PRES | Rotating Presidency of the Council of the European Union |
| PRES Trio | Grouping of three consecutive rotating Presidencies of the Council of the European Union |
| Reitox | Réseau Européen d’Information sur les Drogues et les Toxicomanies |
| SOCTA | Serious and Organised Crime Threat Assessment |
| UN | United Nations |
| UNAIDS | Joint United Nations Programme on HIV/AIDS |
| UNGASS | United Nations General Assembly Special Session |
| UNODC | United Nations Office on Drugs and Crime |
| **UNDP** | **United Nations Development Programme** |
| ~~WCO~~ | ~~World Customs Organisation~~ |
| WHO | World Health Organisation (UN) |

1. OJ C 402, 29.12.2012, p. 1. [↑](#footnote-ref-1)
2. OJ C 351, 30.11.2013, p. 1. [↑](#footnote-ref-2)
3. COM(2015) 185. [↑](#footnote-ref-3)
4. A consortium composed of Ernst & Young and RAND Europe. [↑](#footnote-ref-4)
5. <http://ec.europa.eu/dgs/home-affairs/what-is-new/work-in-progress/initiatives/984ws_intro_en.htm> [↑](#footnote-ref-5)
6. An overview of the results of the evaluation in the form of a Commission Staff Working Document is annexed to this Communication - SWD (2017)95. [↑](#footnote-ref-6)
7. It is not the objective of this Communication to update the EU Drugs Strategy, which remains valid until 2020. The Commission considers that the changes proposed in the new draft Action Plan are in line with the existing Strategy. [↑](#footnote-ref-7)
8. *EU Drug Markets Report 2016*, Europol and EMCDDA. [↑](#footnote-ref-8)
9. *European Drug Report 2016*, EMCDDA. [↑](#footnote-ref-9)
10. This represents an increase on the 2013 figure. [↑](#footnote-ref-10)
11. The source for all data in the paragraph is the *European Drug Report 2016*, EMCDDA. [↑](#footnote-ref-11)
12. Including FP7, Horizon 2020 and Health Programme 2014-2020 [↑](#footnote-ref-12)
13. This involved over 90 interviews with representatives from all EU Member States, European institutions, agencies, third countries, and other stakeholders; an online survey of European External Action Service (EEAS), representatives in non-EU countries; an online public consultation and roundtable discussion with representatives from the Civil Society Forum on Drugs. [↑](#footnote-ref-13)
14. This is due to the fact that not all Member States provide data on all measures, to the fact that different indicators cover different time periods, that some indicators are based on registers or surveys and are quantifiable while others rely on expert opinions or qualitative assessments. [↑](#footnote-ref-14)
15. Interviews, surveys, desk research, public consultation, roundtable discussions. [↑](#footnote-ref-15)
16. [Joint statement by the Council and the representatives of the governments of the Member States meeting within the Council, the European Parliament and the Commission on European Union Development Policy: ‘The European Consensus’ OJ C/46/1 of 24.02.2006](http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=OJ%3AC%3A2006%3A046%3A0001%3A0019%3AEN%3APDF) [↑](#footnote-ref-16)
17. [COM (2007) 630 final](https://ec.europa.eu/health/ph_overview/Documents/strategy_wp_en.pdf) and objectives identified in 2007 will remain valid for the next decade in the context of Europe 2020. In addition the [Third Health Programme 2014-2020](http://ec.europa.eu/health/programme/policy_en) points to similar challenges [↑](#footnote-ref-17)
18. A new action 3 was introduced and action 4 has been updated. [↑](#footnote-ref-18)
19. Action 5 has been updated: it now refers to the 'misuse of psychoactive medicines'; this includes any type of psychoactive/addictive substances used for treatment, all drugs acting on the central nervous system and opioids and medicines used in opioid substitution treatment. [↑](#footnote-ref-19)
20. Actions 6 and 7 have been updated [↑](#footnote-ref-20)
21. Objective 2, several actions under the drug demand reduction pillar and action 48 have been amended to reflect this development. In this context, it is suggested that synergies be explored with the European Solidarity Corps. [↑](#footnote-ref-21)
22. Actions 8 and 9 have been strengthened to reflect the central objective of the EU's positions for UNGASS. [↑](#footnote-ref-22)
23. Council conclusions on the implementation of the EU Action Plan on Drugs 2013-2016 regarding minimum quality standards in drug demand reduction in the European Union 11985/15 [↑](#footnote-ref-23)
24. Action 10 has been updated [↑](#footnote-ref-24)
25. Action 11 has been updated [↑](#footnote-ref-25)
26. Council conclusions on improving the monitoring of drug supply in the European Union 15 November 2013 [↑](#footnote-ref-26)
27. Action 17 has been updated [↑](#footnote-ref-27)
28. Action 19 has been updated [↑](#footnote-ref-28)
29. Action 20 has been amended accordingly [↑](#footnote-ref-29)
30. Regulation (EC) No 273/2004 of the European Parliament and of the Council on drug precursors (OJ L 47, 18.2.2004, p. 1–10) and Council Regulation (EC) No 111/2005 laying down rules for the monitoring of trade between the Union and third countries in drug precursors (OJ L 22, 26.01.2005, p. 1-10) [↑](#footnote-ref-30)
31. *Study on alternatives to coercive sanctions as response to drug law offences and drug-related crimes*, May 2016, for the European Commission [↑](#footnote-ref-31)
32. Action 22 has been updated [↑](#footnote-ref-32)
33. Action 23 has been updated. The challenges are driven by factors such as secure encryption, web hosting, the move from surface to deep websites and/or the darknet; the emergence of new forms of payment (such as bitcoins); and the growth in drug advertising and exchanges on social media. Particular attention has been given to the use of the web for the sale of prescription drugs and NPSs. [↑](#footnote-ref-33)
34. Report from "Internet and drugs" expert meeting June 2016 [↑](#footnote-ref-34)
35. Action 24 has been amended in line with the evaluation’s recommendation that the current coordination mechanisms between the HDG and the Standing Committee on Operational Cooperation on Internal Security (COSI) be reviewed. In addition, actions 24 and 28 (as amended) also address the need to improve coordination between the HDG and thematic Council Working Groups of the Council, e.g. those on the UN Working Party and Human Rights. This would improve synergies and cooperation on international relations, especially in the framework of the 2019 review process of the 2009 UN Political Declaration and Action Plan on International Cooperation towards an Integrated and Balanced Strategy to Counter the World Drug Problem. [↑](#footnote-ref-35)
36. Action 26 has been updated [↑](#footnote-ref-36)
37. Action 31 has been updated [↑](#footnote-ref-37)
38. Action 34 has been amended to give full support to EU Delegations’ role in monitoring drugs policy developments in non-EU countries and reporting back to the Commission and the European External Action Service (EEAS). [↑](#footnote-ref-38)
39. Former actions 34 and 35 have been merged in action 35 since they addressed similar issues: illegal drug crop cultivation and alternative development continue to be of interest. [↑](#footnote-ref-39)
40. Action 38 has been updated; in the light of renewed diplomatic relations, Iran has been added to the list of countries with which the EU will seek closer cooperation and conduct dialogues on drugs. [↑](#footnote-ref-40)
41. The Dublin Group is a flexible, informal consultation and coordination mechanism for global, regional and country-specific problems of illicit drugs production, trafficking and demand. It is based on consensus and mutual assistance. Its participants are the EU Member States, Australia, Canada, Japan, Norway, the United States, the European Commission and the UNODC. [↑](#footnote-ref-41)
42. Action 39 has been updated [↑](#footnote-ref-42)
43. Former action 40 has been deleted. [↑](#footnote-ref-43)
44. Action 41 has been updated. [↑](#footnote-ref-44)
45. Action 45 has been updated. [↑](#footnote-ref-45)
46. Action 46 has been updated. [↑](#footnote-ref-46)
47. Idem 8. [↑](#footnote-ref-47)
48. New action 47. [↑](#footnote-ref-48)
49. COM (2015) 285 final. [↑](#footnote-ref-49)
50. COM (2012) 286 final. [↑](#footnote-ref-50)
51. Action 48 was updated. Cannabis is the most widely used drug in the EU. Recent years have seen a number of developments in some non-EU countries with regard to cannabis law reform, e.g. as de-penalisation of use, market regulation or legalisation. [↑](#footnote-ref-51)
52. Action 52 has been updated. [↑](#footnote-ref-52)
53. Reitox is the European information network on drugs and drug addiction. It was created at the same time as the EMCDDA and is made up of ‘national focal points’ or ‘national drug observatories’ (designated national institutions or agencies responsible for collecting data and reporting on drugs and drug addiction. [↑](#footnote-ref-53)
54. Regulation (EC) No 1920/2006 of the European Parliament and of the Council of 12 December 2006 on the European Monitoring Centre for Drugs and Drug Addiction (recast) [↑](#footnote-ref-54)
55. **The draft Action Plan includes in bold newly added parts and in strikethrough the parts that the Commission proposes to remove** [↑](#footnote-ref-55)
56. **Evidence based should be read in this context as "based on available scientific evidence and experience"** [↑](#footnote-ref-56)
57. Council conclusions on the implementation of the EU Action Plan on Drugs 2013-2016 regarding minimum quality standards in drug demand reduction in the European Union 11985/15 [↑](#footnote-ref-57)
58. **The Maritime Analysis and Operations Centre – Narcotics (MAOC (N), based in Lisbon, is an initiative by 7 EU Member Countries: France, Ireland, Italy, Spain, Netherlands, Portugal and the UK and is co-funded by the Internal Security Fund of the European Union. The Centre provides a forum for multi-lateral cooperation to suppress illicit drug trafficking by sea and air.** [↑](#footnote-ref-58)
59. **Council conclusions on improving the monitoring of drug supply in the European Union 15 November 2013** [↑](#footnote-ref-59)
60. **Directive 2014/42/EU of the European Parliament and of the Council on the freezing and confiscation of instrumentalities and proceeds of crime in the European Union; Council Decision 2007/845/JHA concerning cooperation between Asset Recovery Offices of the member States in the field of tracing and identification of proceeds of, or other property related to, crime; Council Framework Decision 2006/783/JHA on the application of the principle of mutual recognition to confiscation orders. Council Framework Decision 2003/577/JHA on the execution in the European Union of orders freezing property or evidence, Commission proposal for a Regulation of the European Parliament and of the Council on the mutual recognition of freezing and confiscation orders COM(2016) 819; Council Framework Decision 2005/212/JHA on confiscation of crime-related proceeds, instrumentalities and property; Council Framework Decision 2003/577/JHA on the execution in the European Union of orders freezing property or evidence.**  [↑](#footnote-ref-60)
61. **Directive (EU) 2015/849 of the European Parliament and of the Council on the prevention of the use of the financial system for the purposes of money laundering or terrorist financing, amending Regulation (EU) No 648/2012 of the European Parliament and of the Council, and repealing Directive 2005/60/EC of the European Parliament and of the Council and Commission Directive 2006/70/EC; Council Framework Decision 2001/500/JHA on money laundering, the identification, tracing, seizing and confiscation of instrumentalities and the proceeds of crime. Commission proposal for a Directive of the European Parliament and of the Council on countering money laundering by criminal law COM (2016) 826.Regulation (EU) 2015/847 of the European Parliament and of the Council on information accompanying transfers of funds and repealing Regulation (EC) No 1781/2006; Regulation (EC) No 1889/2005 of the European Parliament and of the Council on controls of cash entering or leaving the Community. Commission proposal for a Regulation of the European Parliament and of the Council on controls on cash entering or leaving the Union and repealing Regulation (EC) No 1889/2005** [↑](#footnote-ref-61)
62. **Council Framework Decision 2004/757/JHA of 25 October 2004 laying down minimum provisions on the constituent elements of criminal acts and penalties in the field of illicit drug trafficking, as regards the definition of drug** [↑](#footnote-ref-62)
63. **Council Conclusions on improving criminal justice in cyberspace 09 June 2016** [↑](#footnote-ref-63)
64. Under Horizon 2020 (2014-2020), some €27 million have already been allocated to projects addressing drug addiction and include behavioural research and neuroscience [↑](#footnote-ref-64)
65. These indicators are based on existing reporting systems that pre-date the objectives of the current EU drug strategy and action plan, but provide the most comprehensive set of EU level resources to support their monitoring and evaluation [↑](#footnote-ref-65)