

**ANNEX**

Status of delivered outputs under the third EU Work Plan for Sport (2017-2020)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Priority 1 – Integrity of Sport** | | | | |
| **Key topic: Anti-doping** | | | | |
| **Activity** | **Output** | **Target date** | **Leader(s)** | **Status** |
| 1 | Council and its preparatory bodies Expert input in anti-doping issues to be prepared by meetings of experts and to be discussed at the Working Party on Sport, in particular compatibility with EU law, regarding any forthcoming revision of the WADA Anti-doping Code | 2017-2019 | Commission Presidency | Done |
| 2 | Preparation of the EU and its Member States' position for the CAHAMA and WADA meetings supported as necessary by meetings of experts. | 2017-2020 | Commission Presidency | Ongoing |
| 3 | Seminar - Ways of preventing the use of doping by young people in professional and in grassroots sports | 2nd half 2017 | Commission | Done |
| **Key topic: Good governance** | | | | |
| 4 | **Expert Group – Integrity**   * Application of international recognised good governance and anti-corruption standards and initiatives in particular from outside sport to be applied in the field of sport * Match fixing | 2018-2020 | Commission | 5 meetings organised |
| 5 | Council and its preparatory bodies - Recommendations on possible future actions against corruption in sport at the EU level. | 2nd half 2019 | Presidency | Done |
| **Key topic: Safe-guarding of minors** | | | | |
| 6 | Study - Prevalence of child abuse in sport | 1st Half 2019 | Commission | Done |
| 7 | Seminar - Follow-up of the Recommendations on the protection of young athletes and safeguarding children’s rights in sport | 2nd Half 2019 | Presidency | Done |
| 8 | Council and its preparatory bodies -Protecting physical and moral integrity of minors in grassroots and elite sport. | 2nd Half 2019 | Presidency | Done |
| **Key topic: Specificity of sport** | | | | |
| 9 | Group of interested Member States - EU law in relation to sport and sport organisations | 1st half 2019 | SE, FR, ES, NL | Cancelled |
| 10 | Seminar - Specificity of sport within the EU | 2nd half 2019 | Commission | Done |
| **Priority 2 – The Economic Dimension of Sport** | | | | |
| **Key topic: Innovation in sport** | | | | |
| 11 | Cluster meeting - The economic benefits of sport through Sport Satellite Accounts (SSA). The practical use of SSAs for sport policy makers. | 1st Half 2018 | Commission | Done |
| 12 | Raise awareness of the economic dimension of sport in particular with regard to the Europe 2020 Strategy - focusing on the economic benefits of sport and innovation | 2nd Half 2018 | Presidency | Done |
| 13 | Conference - Raise awareness of the economic dimension of sport in particular with regard to the Europe 2020 Strategy - focusing on the economic benefits of sport and innovation | 2nd Half 2018 | Presidency | Done |
| **Key topic: Sport and the digital market** | | | | |
| 14 | Seminar - The benefits and challenges of the digital single market for a better funding and commercialisation of sport | 1st Half 2019 | Presidency | Cancelled |
| **Priority 3 – Sport and Society** | | | | |
| **Key topic: Sport and media** | | | | |
| 15 | Conference - Role and influence of media in sport | 1st Half 2020 | Presidency | To be organised |
| 16 | Council and its preparatory bodies Role and influence of media in sport | 1st Half 2020 | Presidency | Cancelled |
| **Key topic: Role of coaches** | | | | |
| 17 | Council and its preparatory bodies - Role of coaches in society | 2nd Half 2017 | Presidency | Done |
| 18 | Conference - Role, status and responsibility of coaches in society | 2nd Half 2017 | Presidency | Done |
| **Key topic: Education in and through sport** | | | | |
| 19 | Conference - Physical activity, sport and athlete’s dual career with the focus on university and education | 2nd Half 2017 | Presidency | Done |
| 20 | Expert Group - Skills and human resources development in sport. | 2018-2020 | Commission | 5 meetings organised |
| 21 | Seminar - Sport qualifications and competences for coaches | 1st Half 2020 | Presidency | Done |
| **Key topic: Social inclusion** | | | | |
| 22 | Council and its preparatory bodies -Promoting European values through sport | 1st Half 2018 | Presidency | Done |
| 23 | Conference - Grassroots sport as a tool for integration and a bridge between tradition and innovation | 1st Half 2018 | Presidency | Done |
| 24 | Study - Access to sport for people with disabilities | 2nd Half 2018 | Commission | Done |
| 25 | Council and its preparatory bodies - Access to sport for people with disabilities. | 1st Half 2019 | Presidency | Done |
| 26 | Conference - The advantages of practising sport in an organised environment for people with fewer opportunities | 1st Half 2019 | Presidency | Done |
| 27 | Cluster meeting - Promoting health enhancing physical activity | 2nd Half 2017 | Commission | Done |
| **Key topic: Sport and health** | | | | |
| 28 | Seminar - Sport and physical activity at the work place | 2nd Half 2018 | Presidency | Done |
| **Key topic: Sport and environment** | | | | |
| 29 | Group of interested Member States - Urban development, nature sport, environmental sustainability in the context of major sporting events, environmentally sound and energy efficient sport facilities | 2018-2020 | FR, DE, PT | Done |
| **Key topic: Sport diplomacy** | | | | |
| 30 | Study - Sport in support of EU external relations | 2nd Half 2017 | Commission | Done |
| 31 | Seminar - Follow up of the Commission High Level Group, Council conclusions of November 2016 and Seminar on Sport Diplomacy | 2nd Half 2017 | Commission | Done |