EUROPEAN CONSENSUS ON HUMANITARIAN AID - ACTION PLAN

| ACTION AREA ONE: ADVOCACY, PROMOTION OF HUMANITARIAN PRINCIPLES AND INTERNATIONAL LAW |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: EU strengthened commitment to ensuring neutral and independent humanitarian action and to protecting humanitarian space |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative timing | Output |
| Priority actions: |  |  |  |  |  |
| §16, 97 | 1 | High-level international conference on current International Humanitarian Law issues and challenges for humanitarian aid in practice, linked to reinforced advocacy and awareness raising activities (cf below). | EU | 2008 | Conference organised. |
| §16 | 2 | General and case-specific advocacy for the respect of international law, including International Humanitarian Law, Human Rights Law and Refugee Law through EU policy channels (statements, political dialogue, joint demarches). | EU | ongoing | Specific situations of failure to uphold IHL are raised with responsible parties. |
| §10, 16 | 3 | Uphold the fundamental humanitarian principles through EU coordinated positions promoting neutral independent and impartial humanitarian action in all relevant international bodies, and reinforce awareness of the application of those principles across governments and institutions. | EU | ongoing | EU statements. EU external action in accordance with humanitarian principles and adherence to UN MCDA/Oslo guidelines. |
| Additional actions: |  |  |  |  |  |
| §16 | 4 | Operationalising the EU guidelines on promoting compliance with International Humanitarian Law. | EU | 2009 | EU Member States agree practical steps for ensuring application of these guidelines. Implementation of EU joint pledges in follow-up to 30th International Conference of the Red Cross and Crescent. |
| §10, 16 | 5 | Develop material for supporting improved understanding and awareness of humanitarian principles: - draw-up short humanitarian principles 'aide-memoire' for advocacy purposes; - guidance to ensure humanitarian dimension is duly considered in all EU external action; - develop EU training directory/pack (multipurpose and for use with a range of actors) on humanitarian principles and IHL implications for humanitarian assistance to be disseminated through training and workshops within EU institutions; - further efforts to promote understanding of the Guidelines on the Use of Military and Civil Defence Assets in complex emergencies and the Oslo Guidelines on the Use of Military and Civil Defence Assets in International Disaster Relief, including dissemination of the Field Handbook; - assess impact of dissemination and awareness-raising activities, including public communication. | EU | 2009 2009 on | Standard material developed and disseminated through varied channels to different audiences, including through incorporation in training activities. |

| ACTION AREA TWO: IMPLEMENTING QUALITY AID APPROACHES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: Humanitarian needs identified and met more effectively, with increased focus on neglected crises and specific vulnerabilities and results-oriented approaches. Aid delivered to best possible quality standards and with good levels of accountability. |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative Timing | Output |
| Priority actions: |  |  |  |  |  |
| §27, 31-32 | 6 | Support OCHA in definition of a common methodological framework for needs assessment. Dissemination of results to EU Member States and field experts and partners. | EC | ongoing | OCHA study on needs assessment supported leading to finalisation of common framework and improved common understanding of needs assessment. |
| §28, 42, 97 | 7 | Rolling programme of sectoral areas for further collaborative work, leading to operational recommendations, with sectoral priorities reviewed regularly: | EC |  | EC operational guidelines on sectoral issues, which would be available for MS donors to use as appropriate. Increased systematic sharing of expertise. |
|  | i) | children in emergencies; |  | ongoing |  |
| §35 | ii) | use of cash and vouchers in humanitarian response; |  | 2008-9 |  |
|  | iii) | Humanitarian aid funding interventions relating to HIV-AIDS; |  | 2008-9 |  |
|  | iv) | overview of protection strategies (including protection against sexual and gender based violence) and funding protection; |  | 2008-9 |  |
|  | v) | gender mainstreaming in Humanitarian Aid, including review of current tools available. |  | 2009-10 |  |
| §37-38, 96 | 8 | EU budget review – financial perspectives (mid-term): assessment of adequacy of resources for humanitarian aid in light of increased needs and overall increases in ODA. Long-term trends in need and humanitarian aid as part of the aid continuum to be duly considered in assessing the resources available for Relief. | EU | 2009 | EC Humanitarian Aid Budget sufficient to make substantial contribution to meeting increased humanitarian needs. |
| §27-28, 33 | 9 | Annual exchange of info on EU MS humanitarian response policies and intervention strategies, linked to presentation of DG ECHO Strategy | EU | 2009 on | Annual discussion in Council that allows for increased synergies between EU donor strategies. |
| §75-76 | 10 | Review existing studies on the impact of climate change on Humanitarian Aid and make recommendations, ensuring linkage to overall EU approach. | EU | 2009 | Review completed - contributing to increased understanding of how climate change may affect need for humanitarian aid, with recommendations of how aid approaches may need adapting accordingly. |
| §97 | 11 | Increase efficiency of EC humanitarian aid governance within the current regulatory framework. | EC | 2009 on | Review of possible efficiency gains is undertaken. |
| Additional actions: |  |  |  |  |  |
| §27, 31-33 | 12 | Widen dissemination of the EC Global Needs Assessment and Forgotten Crisis Assessment. Review and revise methodology as appropriate. | EC | ongoing | Methodology systematically applied, disseminated and refined to be the best possible index of global vulnerability. Funding decisions are based on assessed need, and balance of response between crises according to need remains in focus. |
| §34 | 13 | Elaborate diversified approaches and interventions to food assistance and livelihoods support responses in different contexts on the basis of an improved needs assessment analysis. | EC | ongoing | Action taken to adjust policy and financing to contexts and needs. |
| §47, 97 | 14 | Improve evaluation methodology, dissemination and use and develop methodology to promote joint evaluations and develop user-oriented terms of reference that include standard requirement for assessment of local population views (where field visits included). | EC | 2008-9 | Evaluation methodology updated and shared with other donors. New Terms of Reference finalised. |
| §40 | 15 | Review modalities and conditions for EC primary emergency decisions and further increase efficiency of decision-making process for EC financing decisions. | EC | 2010 | Review undertaken. |
| §40-41 | 16 | Organise EU expert discussion on how to promote further knowledge of the different tools available and explore value-added of producing a CD/ROM on quality standards in Humanitarian Aid for wide dissemination. | EU | 2010 | Expert meeting on promotion of quality standard tools, leading to further dissemination of relevant standards. |
| §40, 43-44 | 17 | EU expert dialogue on measurability (introducing results-oriented management) - leading to the establishment of a set of performance indicators to be integrated as appropriate into Humanitarian Aid funding agreements. This would involve the further development of analytical tools on impact (outcome) of humanitarian interventions. | EU | 2011 | Common set-of performance indicators and analytical tools on impact developed. |

| ACTION AREA THREE: REINFORCING CAPACITIES TO RESPOND |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: Improved rapid and appropriate response to humanitarian crisis, with international assistance reinforcing local action as first line of response |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative Timing | Output |
| Priority actions: |  |  |  |  |  |
| §25, 54-56, 97 | 18 | Comprehensive mapping study on logistical capacity and EU support, including stockpiling, procurement and transport to area of final use of humanitarian goods. Discussion on results and recommendations of study and indications of areas that require further support at international level. | EU | 2009 | Mapping study finalised to be followed by expert meeting and possible operational recommendations. EU support for strengthened logistical capacity of the international humanitarian system. |
| §53-56, 67,70, 74 | 19 | Explore how to enhance support to capacity building, including in the cluster approach and provisions for reinforcing local capacity. Promote a multi-donor approach to capacity building (partners, non-EU donors and other stakeholders to be consulted). | EU | 2009 on | EC evaluation of Thematic Financing completed, feeding in to reflection on capacity-building support. Donors engaged in expert dialogue on capacity building leading to strengthened overall EU support. |
| §§26, 40-41,45, 97 | 20 | Reinforcement of EU training provision for humanitarian professionals and other actors linked to humanitarian response, with strong emphasis on operational aspects. This should include: - strengthening EU humanitarian aid departments and field staff training strategies, including joint training activities on issues identified as priority; - conducting a seminar programme aimed primarily at newly acceded EU Member States institutions and civil society; - a review the Network on Humanitarian Assistance (NOHA) Master's programme and other vocational training provision, with possible recommendations for strengthening overall EU support, linking also to local capacity; - linkage to other existing humanitarian training provision, such as UNDAC. | EU | 2010 | Review of existing training needs, provision and suitability completed with a view to reinforcement of professional humanitarian operational capacity. Synergies identified and quality joint training initiatives undertaken as appropriate. |
| Additional actions: |  |  |  |  |  |
| §40 | 21 | Promote and provide support to International Disaster Response Laws, Rules and Principles. | EU | 2010 | Improved EU understanding of IDRL and how its implementation can be promoted to facilitate humanitarian operations. |
| §26, 97 | 22 | Explore with MS the possibility of establishing a short 'twinning/job-shadow' programme in MS humanitarian departments or in the EC for new Member State humanitarian aid officials to reinforce best practice exchange between EU donors. | EU | As arising | Exchange of officials between a number of EU humanitarian aid departments and strengthened contacts across EU. |

| ACTION AREA FOUR: STRENGTHENING PARTNERSHIP |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: strengthened well-coordinated partnerships for effective delivery of aid, expanded donor base, reinforcement of local participation in humanitarian aid design and implementation. |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative Timing | Output |
| Priority actions: |  |  |  |  |  |
| §20, 29, 67, 73 | 23 | Active EU participation in humanitarian fora (international, regional) and thereby contribute to reinforced dialogue involving broad range of partners and current and emerging donors at the international level. | EU | ongoing | Without prejudice to respective competences and traditions, possibility for EU coordination ahead of major humanitarian meetings used to its full added-value with strengthened common understanding of main messages and priorities for international debate. |
| §18-20 | 24 | All EU donors to work towards mainstreaming GHD commitments in humanitarian action. Take steps to facilitate the participation of all EU Member States/EC in GHD donor-coordination working methods, including setting-up informal 'GHD-mentoring' between well-established and newer EU donors. | EU | 2008-9 | GHD principles adhered to in practice by all EU donors and good practices pursed actively through shared learning and peer review. Newer EU donors engaged into GHD. |
| §43, 46, 53 | 25 | Preliminary review of existing practices to ensure participation of disaster-affected communities in Humanitarian Aid operations, leading to a more detailed joint evaluation of the participation of affected populations in EU Humanitarian Aid programmes. Draw up recommendations for strengthening this as appropriate. | EU | 2009-11 | Review undertaken, followed by evaluation and operational recommendations for consideration by EU donors. |
| Additional actions: |  |  |  |  |  |
| §18-19 | 26 | Provide further encouragement to UN, Red Cross Movement and humanitarian NGO partners (including local partners) in application of the Principles of Partnership of the Global Humanitarian Platform. | EU | Ongoing | EU donor advocacy in support of application of the Principles of Partnership, to reinforce explicit EU recognition of the plurality of implementing partners and the need for good operational cooperation and coordination between partners. |
| §30, 49 | 27 | Establish EC-Partner Policy Liaison Groups | EC | 2008 | Groups used to provide quality input for key areas of policy implementation under the European Consensus on Humanitarian Aid. |
| §97 | 28 | Put in place a Good Humanitarian Donorship 'implementation plan' | EC | 2009 | GHD implementation plan finalised. |
| §97 | 29 | Facilitate organisation of humanitarian days in the European Union | EU | 2010 | Humanitarian days organised. |

| ACTION AREA FIVE: ENHANCING COHERENCE AND COORDINATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: better linkages between EU donors and others to improve efficiency of overall EU aid contribution. Strengthened liaison between actors present in the field in response to Crisis. Humanitarian considerations fully taken into account in other related EU policy areas. |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative Timing | Output |
| Priority Actions: |  |  |  |  |  |
| §25, 65 | 30 | Support UNOCHA to deploy civil-military liaison officers in situations of crisis, and where most needed EC to consider deploying field experts with appropriate profile to reinforce civil-military liaison. | EU | As appropriate | Civil-military liaison offices in place where needed in all major crises. |
| §22, 27-28 | 31 | Following endorsement of the mandate of the Humanitarian Aid and Food Aid Working Group (to be convened from 1 January 2009), prepare priorities for regular policy discussion in the group, including on implementation of the European Consensus on Humanitarian Aid. | EU | 2008-9 | Group established and playing an effective role at centre of EU policy dialogue on humanitarian aid. |
| §27-28 | 32 | EU donor coordination mid-year review of funding/needs and regular exchange on general funding intentions/patterns through EU level strategy exchange, with appropriate linkage to dialogue with other major non-EU donors through existing international donor coordination mechanisms. | EU | 2009 | Annual discussion in Humanitarian Aid and Food Aid working group, with improved information flow on donor response to humanitarian needs. |
| §99, 101 | 33 | Mid-term review of Action Plan and implementation of Consensus – in dialogue with EP and Partners. | EU | 2010 | Mid-term review exercise finalised with assessment of implementation results and output. |
| §101 | 34 | Undertake review of EU Consensus implementation and consider successor Action Plan – in dialogue with EP and Partners. | EU | 2012 | Full-term review with recommendations for future work. |
| Additional actions: |  |  |  |  |  |
| §57-60 | 35 | Continued dialogue between EU humanitarian and civil protection actors in accordance with provisions of the European Consensus on Humanitarian Aid. | EU | ongoing | Enhanced understanding of UN MCDA/Oslo guidelines, reinforcement of needs-based approach and strengthened coordination between different actors. |
| §27-28 | 36 | From the field, EC to reinforce its facilitation role in information sharing, situation analysis and coordination with EU Member States, linked closely to other major non-EU donors as well as to implementing partners, and avoiding duplication with existing coordination mechanisms. | EC | 2008 on | Reinforced information-sharing between donors. |
| §27-28 | 37 | Ensure more regular expert-level dialogue on implementation issues and coordination of EU responses to major humanitarian crises. | EU | 2008 on | Improved EU common understanding of operational challenges and better coordination of EU donor response to major and sudden-onset crises. |
| §65 | 38 | Facilitate launch of dialogue between EU Military Staff and humanitarian Non-Governmental Organisations on their relations in emergencies. | EU | 2008 on | Appropriate links established between EU Military Staff and humanitarian NGOs including, as needed, in the field. |
| §27-28 | 39 | Establish EU humanitarian aid - general overview paper and updated contacts, including field representatives. | EU | 2008 | Overview and contacts lists established and maintained. |
| §27, 47, 73 | 40 | Annual meeting of EU evaluation experts to present trends and findings and undertake more joint evaluations (establish a rolling-programme of priorities of common interest led by different donors). | EU | 2008 on | EU evaluation experts' network in place, evaluation plans and results shared more systematically and increased number of joint evaluations undertaken. |
| §72, 95 | 41 | Written guidance and refresher training for EU Member States on reporting to 14 points, where possible together with OCHA on FTS and assess system performance and propose improvements in functioning. | EC | 2009 | Guidance note and training provided – leading to improvements in recording of humanitarian aid contributions. |
| §22, 26 | 42 | Establish system for 'humanitarian briefing' (HQ welcome note/field experts) for newly-posted Embassy and Delegation officials in crisis prone countries and regional humanitarian hubs. | EU | 2009 | Briefing arrangements on humanitarian action for priority Embassy/Delegations in place and maintained. |

| ACTION AREA SIX: THE AID CONTINUUM |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Expected overall result: Humanitarian aid is focussed on emergency response in response to humanitarian needs and linked better with longer-term development and other assistance. Disaster Risk Reduction activities are strengthened and supported increasingly by long-term aid approaches. |  |  |  |  |  |
| Consensus Ref. | Action No. | Actions proposed | EU/EC | Indicative Timing | Output |
| Priority Actions: |  |  |  |  |  |
| §22, 75-76 | 43 | Develop an EU strategy on support to mainstreaming of Disaster Risk Reduction in developing countries linked with ongoing projects that include community-based disaster preparedness activities and with EU strategy on climate change, including development of guidance and practical DRR tools. | EU | 2008-9 | EU DRR Strategy agreed upon, in support of international efforts within the Hyogo Framework for Action. |
| §22, 30, 77-78 | 44 | Identify rolling list of countries requiring priority LRRD focus in EU support, and exchange best practice examples of LRRD. | EU | 2009 on | Priorities list established, best practice awareness increased and reinforced focus provided on EU support to LRRD. |
| §22, 30, 77-78 | 45 | Review range of transition mechanisms at an EU level and make recommendations for further improvements. | EU | 2010 | Review undertaken with recommendations considered. |
| Additional actions: |  |  |  |  |  |
| §22, 30, 77-78 | 46 | Ensure regular field and HQ co-ordination for LRRD with particular attention to focus countries and reinforced cooperation between humanitarian and development agencies at field level. | EU | Ongoing | More active coordination between development and humanitarian aid actors and national/local authorities to facilitate LRRD (including at a field level in early recovery cluster or ad hoc working group where cluster not in place). |
| §22, 30, 77- 78 | 47 | Finalise and implement a framework for country situation analysis for LRRD to ensure a consolidated response with aim of ensuring LRRD activities are integrated into existing Country Strategies as early as possible through dialogue and coordination with national and local authorities. | EC | Ongoing | Framework established and country strategies integrate support to early recovery allowing smooth and timely 'exit' from emergency relief aid provision. |
| §22, 26, 30-32 77- 78 | 48 | Promote discussion with Partners on linkage between relief and recovery phase needs assessments: the humanitarian needs assessment framework, Post-Conflict Needs Assessment and Post-Disaster Recovery Damage and Needs Assessment. | EU | 2009 | Experts/Partners meeting on different needs assessment approaches leading to improved understanding of linkages. |
| §75-76 | 49 | Promote strengthened EU operational contacts and policy dialogue on Disaster Risk Reduction priorities and best practice to further ensure complementarities, involving humanitarian aid and development experts and partners. | EU | 2009 on | EU DRR network with operational focus reinforced. |