EN

|  | COMMISSION OF THE EUROPEAN COMMUNITIES |
| --- | --- |

Brussels, 11.12.2006

SEC(2006) 1628

COMMISSION STAFF WORKING DOCUMENT

Annex to the

REPORT FROM THE COMMISSION TO THE EUROPEAN PARLIAMENT,
THE COUNCIL, THE EUROPEAN ECONOMIC AND SOCIAL COMMITTEE
AND THE COMMITTEE OF THE REGIONS


SAPARD ANNUAL REPORT – Year 2005



{COM(2006) 780 final}

TABLE OF CONTENTS

| ANNEX A: | Financial Execution |  |
| --- | --- | --- |
| ANNEX B: | All Countries |  |
| Table I | Progression of payments |  |
| Table II | All Sapard Countries – EU allocation and the value of Sapard projects contracted since the start of the programme |  |
| Table III | Eight new Member States – EU allocation, value of Sapard projects contracted and payments since the start of the programme |  |
| Table IV | Bulgaria – EU allocation, value of Sapard projects contracted and payments since the start of the programme |  |
| Table V | Romania – EU allocation, value of Sapard projects contracted and payments since the start of the programme |  |
| Table VI | Number of projects contracted with final beneficiaries |  |
| Table VII | Amounts contracted to projects |  |
| ANNEX C: | Distribution of Sapard funds between measures |  |
| Annex C.1 | Distribution of Sapard funds between measures for eight new Member States |  |
| Annex C.2.1 | Amounts contracted in eight new Member States under rural infrastructure and processing and marketing measures |  |
| Annex C.2.1 | Amounts contracted in eight new Member States under farm investment and diversification measures |  |
| Annex C.3 | Amounts contracted per country |  |
| Annex C.3.1 | CZECH REPUBLIC |  |
| Annex C.3.2 | ESTONIA |  |
| Annex C.3.3 | HUNGARY |  |
| Annex C.3.4 | LATVIA |  |
| Annex C.3.5 | LITHUANIA |  |
| Annex C.3.6 | POLAND |  |
| Annex C.3.7 | SLOVAKIA |  |
| Annex C.3.8 | SLOVENIA |  |
| Annex C.3.9 | BULGARIA |  |
| Annex C.3.10 | ROMANIA |  |
| ANNEX D: | Modification of Sapard programmes |  |
| ANNEX E: | Conferral of Management |  |

ANNEX A – Financial Execution

- Table 1 – Execution of commitment appropriations available in the 2005 budget 
by 31.12.2005 (million EUR)

| Budget lines | Budget 2005 | transfers | total available | executed | % |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 = 5/4 | 7 |
| 05.050101 | 248,8 | +1,5 | 250,3 | 250,3 | 100 | the amount not used under Article 7(4) (1,5 million €) was made available to RO/BG |
| 05.050102 | – | – | – | – | – |  |
| 05.010403 | 1,5 | –1,5 | – | – | – | was made avaialbe for RO/BG under AFA 2005 |
| 05.490403 | – | – | – | – | – |  |
| TOTAL | 250,3 | 0 | 250,3 | 250,3 | 100 |  |

- Table 2 – Execution of payment appropriations available in the 2005 budget 
by 31.12.2005 (million EUR)

| Budget lines | Budget 2005 | transfers | total available | executed | % |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 = 5/4 | 7 |
| 05.050101 | 287,5 | +36,1 | 323,6 | 254,4 | 78,6 | execution of the programmes considerably slowed down in RO and BG during the last 2 quarters 2005 |
| 05.050102 | 290,0 | +271,0 | 561,0 | 557,5 | 99,4 | nearly all new Member States had reached or were close to the 95% ceiling |
| 05.010403 | 1,5 | –1,5 |  |  |  | the amount was made available for the global transfer |
| 05.490403 | – | – | – | – | – |  |
| TOTAL | 579,0 | 305,6 | 884,6 | 811,9 | 91,8 |  |

*	Payment claims submitted by the Sapard beneficiary countries but not paid by the Commission at 31.12.2004.

ANNEX A – Financial Execution

- Table 3 – Commitments, payments and RAL by 31.12.2005

|  | Commitments | Payments from the Commission |  |  | in % of available funds | RAL* |
| --- | --- | --- | --- | --- | --- | --- |
| Country | Total AFAs 2000–2005* | Total payments made until 31.12.2004 | Payments made in 2005 | Payments made since start |  |  |
| 1 | 2 | 3 | 4 | 5 = 3+4 | 6 = 5/2 | 7 = 2–5 |
| Bulgaria | 362 311 633 | 91 041 117 | 67 185 699 | 158 226 816 | 43,7 | 204 084 817 |
| Romania | 967 411 692 | 198 243 313 | 187 200 496 | 385 443 809 | 39,8 | 581 967 883 |
| Total 05.050101 | 1 329 723 325 | 289 284 430 | 254 386 195 | 543 670 625 | 40,9 | 786 052 700 |

|  | Commitments | Payments from the Commission |  |  | in % of available funds | RAL* |
| --- | --- | --- | --- | --- | --- | --- |
| Country | Total AFAs 2000-2003* | Total payments made until 31.12.2004 | Payments made in 2005 | Payments made since start |  |  |
| 1 | 2 | 3 | 4 | 5 = 3+4 | 6 = 5/2 | 7 = 2-5 |
| Czech Rep. | 92 787 704 | 78 815 782 | 9 332 536 | 88 148 318 | 95,0 | 4 639 386 |
| Estonia | 51 043 119 | 46 521 522 | 1 969 441 | 48 490 963 | 95,0 | 2 552 156 |
| Hungary | 160 039 127 | 35 672 520 | 108 584 560 | 144 257 080 | 90,1 | 15 782 047 |
| Lithuania | 125 448 234 | 87 710 171 | 31 465 651 | 119 175 822 | 95,0 | 6 272 412 |
| Latvia | 91 883 502 | 67 401 594 | 19 562 912 | 86 964 506 | 94,6 | 4 918 996 |
| Poland | 709 409 786 | 334 862 363 | 339 076 932 | 673 939 295 | 95,0 | 35 470 491 |
| Slovenia | 26 650 758 | 18 959 975 | 6 358 244 | 25 318 219 | 95,0 | 1 332 539 |
| Slovakia | 76 915 845 | 31 901 358 | 41 168 694 | 73 070 052 | 95,0 | 3 845 793 |
| Total 05.050102 | 1 334 178 075 | 701 845 285 | 557 518 970 | 1 259 364 255 | 94,4 | 74 813 820 |

*	Based on global commitments.

**	€573,5 million which was paid to the Sapard countries include €173,5 million an additional amount transferred by the budgetary authority. Payment claims amounting to €86,5 million remained pending in 2004 due to insufficient funds.

***	Out of €991 million actually paid to the Sapard countries €259 million represented payments on account and €732 represented reimbursement payment based on expenditure declarations.

ANNEX B – All Countries

*	Payments including payment requests in treatment.

ANNEX B – All Countries

*	In 2004 and 2005, only Bulgaria and Romania were allocated further €477,0 million of EU funds.

ANNEX B – All Countries

ANNEX B – All Countries

*	Payments including payment requests in treatment.

**	The amount indicated is partially paid in 2005.

***	In 2004, only Bulgaria and Romania were allocated further € 226,7 million of EU funds.

ANNEX B – All Countries

ANNEX B – All Countries

ANNEX C.1 – Distribution of Sapard Funds between Measures for eight New Members States

*	Based on Financial Tables for the SAPARD Rural Development Plans in force on 31.12.2005.

ANNEX C.2.1 – Amounts Contracted in eight New Members States under Farm Investment and Processing and Marketing Measures

*	Waste Management includes sewerage networks, waste-water treatment plans, collection of classified waste, building of facilities for waste utilizing, waste water purification and disposal and solid waste management.

**	Others includes preparatory activities, expansion of public transport and development of technical infrastructure.

ANNEX C.2.2 – Amounts Contracted in eight New Member States under Diversification and Rural Infrastructure Measures

*Arable Crops include cereals, essential-oil crops, oil crops, grain and flax.	***Others includes crayfish and fish farming, preparatory works, development of sales facilities,

**Animal Production and Products include cattle, pork, sheep, poultry, fattening,	markets, festivals, fairs, production of energy of alternative sources, recycling, alternative	
dairying and milk.	heating material, SMEs and providing additional income sources to farm households.

***Agricultural Production: Investment in Agricultural Production in Poland, which
includes horticultural production, other plant production, and investments connected with	
preparation of products for sale and extension of agricultural production profile, was
included as a separate sector as a result of the manner in which was presented in
Poland's monitoring tables.
****Others include wine, fodder production and greenhouses.

ANNEX C.3.1 – CZECH REPUBLIC

*	based on the Financial Table in force on 31.12.2005.

ANNEX C.3.1 – CZECH REPUBLIC

*Quality control includes Hazard analysis critical control points (HACCP)
	and system of common carcass.

ANNEX C.3.2 – ESTONIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.2 – ESTONIA

ANNEX C.3.3 – HUNGARY

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.3 – HUNGARY

ANNEX C.3.4 – LATVIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.4 – LATVIA

ANNEX C.3.5 – LITHUANIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.5 – LITHUANIA

ANNEX C.3.6 – POLAND

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.6 – POLAND

ANNEX C.3.7 – SLOVAKIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.7 – SLOVAKIA

ANNEX C.3.8 – SLOVENIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.8 – SLOVENIA

ANNEX C.3.9 – BULGARIA

*	Based on the Financial Table in force on 31.12.2005.

ANNEX C.3.9 – BULGARIA

ANNEX C.3.9 – BULGARIA

ANNEX C.3.10 – ROMANIA

*	Based on Finance Table in force on 31.12.2005

ANNEX C.3.10 – ROMANIA

ANNEX C.3.10 – ROMANIA

ANNEX D – Modifications of Sapard programmes

|  | Bulgaria | Czech Rep. | Estonia | Hungary | Latvia | Lithuania | Poland | Romania | Slovakia | Slovenia |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Commission Decision approving the Sapard programme on: | 20.10.2000 | 26.10.2000 | 17.11.2000 | 18.10.2000 | 25.10.2000 | 27.11.2000 | 18.10.2000 | 12.12.2000 | 17.11.2000 | 27.10.2000 |
| 1ST modification of the programmes adopted by the Commission on | 21.05.2002 | 26.02.2002 | 19.12.2002 | 26.11.2002 | 28.11.2001 | 23.12.2002 | 22.04.2002 | 11.07.2002 | 5.03.2002 | 24.11.2003 |
| 2ND modification of the programmes adopted by the Commission on | 27.05.2003 | 12.04.2002 | 13.02.2004 | 21.08.2003 | 31.07.2002 | 09.09.2003 | 05.12.2002 | 27.5.2003 | 31.07.2002 | 20.7.2005 |
| 3RD modification of the programmes adopted by the Commission on | 23.12.2004 | 31.07.2002 | 12.07.2005 | 25.02.2004 | 18.02.2003 | 27.05.2005 | 11.07.2003 | 01.08.2003 | 20.03.2003 |  |
| 4TH modification of the programmes adopted by the Commission on | 07.06.2005 | 23.12.2002 |  | 19.09.2005 | 17.07.2003 |  | 01.08.2003 | 17.09.2004 | 21.08.2003 |  |
| 5TH modification of the programmes adopted by the Commission on | 09.09.2005 | 14.07.2005 |  |  | 13.02.2004 |  | 13.02.2004 | 04.07.2005 | 13.02.2004 |  |
| 6TH modification of the programmes adopted by the Commission on |  | 23.12.2005 |  |  | 14.07.2005 |  | 03.11.2004 |  | 09.09.2005 |  |

ANNEX E – Conferral of Management